## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block | SM/07808 | Retrofitting | Extension of pipeline at Pratappur DANDA PARA, BATHAN PARA, BANGAL PARA, HINDU PARA & ADIBASI PARA of PRATAPPUR (ZONE-I) and its adjoining mouza's Piped W/S Scheme including water tap connection (FHTC) at Babuisol Vill (Goswamibandh Adibashipara Hab.), Kuldiha Vill (Adibashipara Hab.) Lachminnarayanpur Vill (2 Nos. Hab.), Pratappur Vill (2 Nos. Habs.), Radhaballabhpur Vill (1 No. Hab), Ramharipur Vill (2 Nos. Hab.) Radhamohanpur Vill. (1 No. Hab.) at Ausgram-II Block under Burdwan Division, PHE Dte._2ND CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000206/2021-2022 | 6393/BWD | 16/11/2021 | 15/01/2022 | SAIKAT RAY | 44.09 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block | SM/07808 | Retrofitting | Extension of pipeline for providing FHTC at Pratappur CHITIM DANGA, RAMHARIPUR , MUSLIMPARA & DHANDAGHA of PRATAPPUR (ZONE-I) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur (Burdwan North)Sub Division under Burdwan Division, P.H.E. Dte. [Sl-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000566/2021-2022 | 134/DSD | 02/03/2022 | 01/04/2022 | SAIKAT RAY | 4.64 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block | SM/07808 | Retrofitting | Connection from newly constructed Over Head Reservoir to Distribution System & Rising main Pipe Line of PRATAPPUR ( ZONE - I & II ) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block, within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte._2nd Call [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000262/2021-2022 | 689/DSD | 08/12/2021 | 29/12/2021 | S.S. ENTERPRISE | 1.66 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block | SM/07808 | Retrofitting | Extension of pipeline at Babuisole & Gosaibandh village of PRATAPPUR (ZONE-II) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000842/2020-2021 | 173/DSD | 19/02/2021 | 12/03/2021 | RALLY CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.67 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block | SM/07808 | Retrofitting | Extension of pipeline at Kuldiha & Raniganj village of PRATAPPUR (ZONE-II) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000843/2020-2021 | 172/DSD | 19/02/2021 | 12/03/2021 | RELIABLE ENGINEERS CO.-OPERATIVE CONSTRUCTION SOCIETY LTD. | 4.73 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block | SM/07808 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PRATAPPUR Piped Water Supply Scheme at Raniganj (Part), Babuisol (Part), Pratappur (Part), village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. |  |  | ORD/000920/2023-2024 | 5482/BWD | 13/12/2023 | 12/01/2024 | N.S. ENTERPRISE | 10.92 | 0 | 0 | 100
Total | [13 empty] | 70.7 | 0 | 0