## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block | SM/07809 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Takipur Piped Water Supply Scheme at Asinda, Chonari & Takipur Village (Mouza), Ausgram-I Block under Burdwan Division, PHE Dte. (Agreement No. 575/BWD of 2020-2021) | AE(HQs) | J.E. 2 BURDWAN | ORD/000274/2020-2021 | 440/BWD | 19/01/2021 | 05/03/2021 | KOUSIK MALLICK | 36.91 | 33.1 | 89.69 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block | SM/07809 | Retrofitting | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TAKIPUR Piped Water Supply Scheme at Takipur (Part), Asinda (part) & Chanwari (Part) habitation, Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | AE(HQs) | J.E. 2 BURDWAN | ORD/000259/2021-2022 | 6693/BWD | 01/12/2021 | 31/12/2021 | HAMID SK | 20.08 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block | SM/07809 | Retrofitting | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TAKIPUR Piped Water Supply Scheme at Takipur (Part), Asinda (part) & Chanwari (Part) habitation, Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Sl-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000565/2021-2022 | 135/DSD | 02/03/2022 | 01/04/2022 | HAMID SK | 4.78 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block | SM/07809 | Retrofitting | Installation of Sluice Valve, Air Valve and inter connection of Pipeline and allied works to regulate the water supply towards Ashinda & Takipur Village of TAKIPUR and its adjoining mouza's Piped W/S Scheme at Ausgram-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-09] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000852/2022-2023 | 709/DSD | 30/12/2022 | 29/01/2023 | HAMID SK | 4.71 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block | SM/07809 | Retrofitting | Construction of Path way, Drain, Vertical Extension of valve chamber & repairing of OHR connection etc. including shifting of damage pipeline at Head work site of TAKIPUR water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Gr.-H] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000230/2021-2022 | 662/DSD | 22/11/2021 | 22/12/2021 | PAL CONSTRUCTION | 4.02 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block | SM/07809 | Retrofitting | Relaying of pipe line damaged by Construction of Health Centre & construction of road / drain etc. at different location of TAKIPUR and its adjoining mouza's Piped W/S Scheme at Ausgram-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[SL-9] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000047/2023-2024 | 175/DSD | 18/04/2023 | 09/05/2023 | TARAMA AGENCY | 0.77 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block | SM/07809 | Retrofitting | Relaying of pipe line damaged by Construction of Community Centre & construction of road / drain etc. at different location of TAKIPUR and its adjoining mouza's Piped W/S Scheme at Ausgram-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[SL-08] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000046/2023-2024 | 174/DSD | 18/04/2023 | 09/05/2023 | TARAMA AGENCY | 0.91 | 0 | 0 | 100
Total | [13 empty] | 72.17 | 33.1 | 45.87