## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ura Piped Water Supply Scheme at Galsi-II Block | SM/07810 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of URA Piped Water Supply Scheme at Ura (1 No Part & 1 No Habitation), Sarul (2 Nos Habitation) & Adrahati Village (Mouza), Gaisi-II Block under Burdwan Division, PHE Dte..(Agreement No. 95/SE/CC/PHE/Dte of 2020-2021) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000445/2020-2021 | 1087/BWD | 08/02/2021 | 09/04/2021 | M/S PURBASHA | 66.7 | 51.62 | 77.4 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ura Piped Water Supply Scheme at Galsi-II Block | SM/07810 | Retrofitting | Construction of drain and pathway at Head work site of URA piped water supply scheme, Block-Galsi-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, PHE Dte. SL-03 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000529/2022-2023 | 648/DSD | 03/11/2022 | 03/12/2022 | M/S PURBASHA | 3.66 | 3.62 | 98.78 | 1
3 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ura Piped Water Supply Scheme at Galsi-II Block | SM/07810 | Retrofitting | Quotation for new service connection at URA PWSS TW-I under CMD/PHED |  |  | BILL/00215/2024-2025 | BP-2024-25-104 | 03/12/2024 | 03/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.65 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ura Piped Water Supply Scheme at Galsi-II Block | SM/07810 | Retrofitting | Acceptance cum Formal Work Order For the work of " Sinking of 250 x 150mm x 150mtr deapth by DR Rig, Construction of 01 (One) no temporary Kiosk for the necessary arrangement of electrification of Tube Well including laying UPVC distribution system (LDS) and other allied works at URA PWSS, Block-Galsi-II, Dist- Purba Bardhaman under Durgapur W/S Division,PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_3 | ORD/000040/2024-2025 | 753/DWSD | 05/06/2024 | 13/06/2025 | SURAJIT MANDAL | 20.93 | 3.31 | 15.8 | 100
Total | [13 empty] | 97.94 | 58.55 | 59.78