## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block | SM/07817 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC at Amarargarh Mandalpara of AMARARGARH Piped Water Supply Scheme [Retrofitting] under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-08] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000032/2023-2024 | 156/DSD | 13/04/2023 | 04/05/2023 | PARTHA RAY | 0.96 | 0.95 | 98.19 | 100
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block | SM/07817 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC at Amarargarh Dakshinpara of AMARARGARH Piped Water Supply Scheme [Retrofitting] under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-07] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000031/2023-2024 | 155/DSD | 13/04/2023 | 04/05/2023 | RAM MOHAN MUKHERJEE | 0.97 | 0.96 | 98.74 | 100
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block | SM/07817 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amrargarh Piped Water Supply Scheme at Amrargarh (10 Nos Habitation), Dombandi (2 Nos Habitation), Jamtara (2 Nos Habitation) & Panch Mahali Village (Mouza), Ausgram-II Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000103/2021-2022 | 3875/BWD | 27/07/2021 | 25/09/2021 | B.B.C. ENTERPRISE | 91.55 | 73.62 | 80.42 | 100
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block | SM/07817 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC at Amarargarh Ankurepara, Bonpara & Sahapara of AMARARGARH Piped Water Supply Scheme [Rectrofitting] under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-06] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000030/2023-2024 | 154/DSD | 13/04/2023 | 09/01/2025 | SAIKAT RAY | 0.97 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block | SM/07817 | Retrofitting | Acceptance cum Formal work order for the work of " Supplying and Laying of different dia UPVC pipe (LDS) including providing FHTC and Repairing and renovation of existing RCC OHR at Amrargarh under Amarargarh PWSS, Block- Aushgram-II, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_2 | ORD/000041/2024-2025 | 751/DWSD | 05/06/2024 | 01/04/2025 | SAIKAT RAY | 36.37 | 0 | 0 | 100
Total | [13 empty] | 130.82 | 75.52 | 57.73