## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | SM/07824 | Retrofitting | Extension of Pipeline with providing Functional Household Tap Connection (FHTC) at Raibandh, Raykona & Kankora adibasipara of DEBSALA and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-C] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000454/2021-2022 | 75/DSD | 11/02/2022 | 13/03/2022 | BHARAT CONSTRUCTION | 4.33 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | SM/07824 | Retrofitting | Extension of Pipeline with providing Functional Household Tap Connection (FHTC) at Debsala Village,Kankora & Pathuria Adibasipara of DEBSALA and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000456/2021-2022 | 76/DSD | 11/02/2022 | 13/03/2022 | D.M. ENTERPRISE | 4.45 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | SM/07824 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Ausgram-II Block under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000472/2021-2022 | 940/BWD | 17/02/2022 | 19/03/2022 | NANDY UDYOG | 11.82 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | SM/07824 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within command area of DEBSHALA piped water supply scheme at Bagbati (02 Nos. habitation), Kakra, Satla (02 Nos. habitation), Gobindapur (03 Nos Habitation), Debshala (02 Nos. Habitation Part), Kankra (Part) & Paduma (02 Nos. habitation Part) village, Ausgram-II Block under Burdwan Division, PHE Dte. |  | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000563/2020-2021 | 4998/BWD | 10/12/2020 | 10/03/2021 | SAI TUBE CO. | 59.61 | 0 | 0 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | SM/07824 | Retrofitting | Restoration of village and drains at Kakra village for DEBSHALA piped water supply scheme, Block-Ausgram-II under Burdwan Division, PHE Dte. [Gr.-L] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000285/2021-2022 | 669/DSD | 25/11/2021 | 10/12/2021 | SAI TUBE CO. | 3.97 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | SM/07824 | Retrofitting | Restoration of village road and drains at part of RAYKONA & KAKRA for Debshala piped water supply scheme, Block-Ausgram-II under Burdwan Division, PHE Dte. [Gr.-M] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000284/2021-2022 | 668/DSD | 25/11/2021 | 10/12/2021 | SAI TUBE CO. | 3.91 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | SM/07824 | Retrofitting | Relaying of pipe line damaged by construction of road with drain at Kankora and installation of Valves to regulate water supply at Bilashpur & Gobindapur of DEBSALA and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[SL-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000625/2021-2022 | 166/DSD | 16/03/2022 | 15/04/2022 | BHARAT CONSTRUCTION | 2.53 | 0 | 0 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | SM/07824 | Retrofitting | Extension of pipeline of DEBSHALA and its adjoining mouzas piped water supply scheme at Ausgram-II Block within Durgapur Sub-Division under Burdwan Division, PHE Dte. |  | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000771/2020-2021 | 1568/BWD | 22/02/2021 | 08/04/2021 | BHARAT CONSTRUCTION | 41.01 | 40.66 | 99.14 | 0
9 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block | SM/07824 | Retrofitting | Acceptance cum Formal Work Order for Big Dia Tubewell Surging by using suitable air compressor at PH-1 & PH-2 of Debshala PWSS Scheme under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_1 | ORD/000135/2024-2025 | 1212/DWSD | 23/08/2024 | 02/09/2024 | GHOSH & ROY ENTERPRISE | 0.66 | 0 | 0 | 100
Total | [13 empty] | 132.29 | 40.66 | 30.74