## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Connecting, relaying and repairing of distribution main towards Irkona (Node 4 to Node 18) and Mohora village Node 157 to Node 163 with newly reoriented line (from Chainage 8.40 km to 10.74 km of Galsi Gohogram road and from Node 152 to Node 157 beside PMGSY road) within Adra W/S Scheme at Durgapur Sub-Division in Galsi-II Block under Burdwan Division, P.H.E. Dte. (Gr.-'E') | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000966/2020-2021 | 554/DSD | 22/12/2020 | 12/01/2021 | PAL CONSTRUCTION | 2.1 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 05] [Agr. No. 745/BWD of 2020-2021] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000379/2020-2021 | 584/BWD | 25/01/2021 | 09/02/2021 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 4.86 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 05] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000204/2021-2022 | 6264/BWD | 02/11/2021 | 17/11/2021 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 4.86 | 4.86 | 100 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - C) [SL. No. : 07] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000216/2021-2022 | 6194/BWD | 28/10/2021 | 12/11/2021 | LAKSHMIKANTA DAS | 4.86 | 4.86 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mohara vilage (Mohara habitation) of ADRA Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000241/2021-2022 | 673/DSD | 29/11/2021 | 20/12/2021 | KOUSIK MALLICK | 4.83 | 4.83 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila Habitation) of Bagila piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Part-B)[SL NO.-09] | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE.,Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000746/2020-2021 | 585./BWD | 25/01/2021 | 09/02/2021 | HAMID SK | 4.87 | 0 | 0 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 06] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000462/2020-2021 | 585/BWD | 25/01/2021 | 09/02/2021 | BASUNDHARA SOLUTION | 4.86 | 4.86 | 100 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Extension of UPVC pipe line of LDS at Khanhati and Patrahati Mouza for providing FHTC of Adra and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[SL-23] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000844/2022-2023 | 706/DSD | 31/12/2022 | 30/01/2023 | UTPAL NANDI | 4.46 | 4.44 | 99.48 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Carriage of withdrawal stacked DI pipes of rising main from Adrahati to Barsul Divisional store and restoration of damaged pipeline of distribution main for construction of drain, concrete road etc at various point at Khanhati village for providing FHTC within Adra W/S Scheme in Galsi-II Block under Durgapur Sub Division, P.H.E. Dte. [SL-06] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000879/2022-2023 | 732/DSD | 30/12/2022 | 20/01/2023 | SHUBHRA KANTI GHOSH | 0.61 | 0 | 0 | 25
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mohara (Part), Kaitara (Part) and Khanhati (Part) Village of Adra Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000129/2022-2023 | 342/DSD | 30/06/2022 | 21/07/2022 | SHUBHRA KANTI GHOSH | 4.82 | 4.82 | 100 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Relaying and repairing of distribution after widening of PWD road in between Chainage 8.40 km to 10.74 km of Galsi Gohogram road between Node 74 to Node 117 within Adra W/S Scheme at Durgapur Sub-Division in Galsi-II Block under Burdwan Division, P.H.E. Dte.[Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000333/2021-2022 | 03/DSD | 03/01/2022 | 02/02/2022 | SHUBHRA KANTI GHOSH | 4.82 | 0 | 0 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Extension of UPVC pipe line of LDS at Kaitara, Patrahati and Mahara Mouza for providing FHTC of Adra and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000273/2022-2023 | 498/DSD | 12/08/2022 | 11/09/2022 | SHUBHRA KANTI GHOSH | 4.81 | 4.78 | 99.5 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Sinking of 200 mm dia. River Bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Gohogram village Block -Galsi-II, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000269/2022-2023 | 494/DSD | 12/08/2022 | 02/09/2022 | KOUSIK MALLICK | 4.35 | 0 | 0 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Sinking of 200 mm dia River Bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Simasimi village Block -Galsi-I, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000270/2022-2023 | 495/DSD | 12/08/2022 | 02/09/2022 | MUNSHI JAVEDUR JAMAN | 4.35 | 0 | 0 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mohara (Part) Village of Adra Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [SL-12] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000888/2022-2023 | 737/DSD | 30/12/2022 | 20/01/2023 | SHUBHRA KANTI GHOSH | 0.94 | 0.93 | 98.59 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kaitara (Part) Village of Adra Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [SL-11] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000889/2022-2023 | 736/DSD | 30/12/2022 | 20/01/2023 | SHUBHRA KANTI GHOSH | 0.96 | 0.96 | 100 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ADRA Piped Water Supply Scheme at Kaitara village, Galsi-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-9] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000882/2022-2023 | 735/DSD | 30/12/2022 | 20/01/2023 | SHUBHRA KANTI GHOSH | 0.97 | 0.95 | 98.51 | 100
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from distribution system within the command area of ADRA Water Supply Scheme at Adra (Part), Mohara (Part), Kaitara and Patrahati village under JAL SAPNO MISSION under Galsi-II Block in Purba Bardhanan District under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000415/2021-2022 | 384/BWD | 20/01/2022 | 21/03/2022 | SHUBHRA KANTI GHOSH | 69.37 | 69.38 | 100.01 | 1
19 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Providing left out FHTC for making Swajal Gram at Khanhati village within Adra Water supply Scheme in Galsi-II Block under Burdwan Division, P.H.E. Dte.[SL-09] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000033/2023-2024 | 157/DSD | 13/04/2023 | 04/05/2023 | SHUBHRA KANTI GHOSH | 0.97 | 0.96 | 99.24 | 100
20 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Restoration and relaying of damaged pipeline of distribution main for construction of drain, concrete road etc at Ruidaspara (South end) of Adra village for providing left out FHTC at Ruidaspara (South end) within Adra W/S Scheme in Galsi-II Block under Burdwan Division, P.H.E. Dte.[SL-12] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000036/2023-2024 | 160/DSD | 13/04/2023 | 04/05/2023 | SHUBHRA KANTI GHOSH | 0.96 | 0.96 | 99.94 | 100
21 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000043/2024-2025 | 463/DWSD | 17/03/2025 | 17/03/2025 | Resource Division | 0.14 | 0 | 0 | 0
22 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block | SM/07829 | Retrofitting | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at ADRAHATI PWSS under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-I | Junior Engineer_3 | ORD/000249/2026-2027 | 858/DWSD | 25/06/2026 | 25/06/2027 | SHUBHRA KANTI GHOSH | 5.1 | 0 | 0 | 0
Total | [13 empty] | 138.88 | 107.6 | 77.47