## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block | SM/07869 | Retrofitting | Formal Work Order for providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Golgram Piped Water Supply Scheme at Golgram Village (Mouza), Galsi-I Block under Burdwan Division, PHE Dte. [Agreement No. 100/SE/CC/PHE/Dte of 2020-2021.] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000425/2020-2021 | 638/BWD | 25/01/2021 | 26/03/2021 | SHUBHRA KANTI GHOSH | 63.87 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block | SM/07869 | Retrofitting | Making Connection with Rising Main And Over Head Reservoir of Golgram W/S Scheme within Durgapur Sub-Division in Galsi-I Block under Burdwan Division, P.H.E. Dte. [Gr.-G] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000135/2022-2023 | 348/DSD | 30/06/2022 | 15/07/2022 | RANADHIR SINHA | 0.33 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block | SM/07869 | Retrofitting | Construction of approach road from entrance to OHR, Pump House and filling of low land around Over Head Reservoir with carried earth at 1st Tube well site of Golgram & its adjoining mouzas water supply scheme, Block-Galsi-I, under Burdwan Division, PHE Dte. [SL-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000122/2022-2023 | 335/DSD | 27/06/2022 | 27/07/2022 | CHOUDHURY INFRA | 1.86 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block | SM/07869 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of February'23. |  |  | BILL/00117/2023-2024 | 13/JJM | 17/04/2023 | 17/04/2023 | SUJAUDDIN SEKH | 0.36 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block | SM/07869 | Retrofitting | Acceptance cum Formal Work Order for the work of Balance work for Distribution System (CI/DI/UPVC), Earth Work & Concrete Work for GOLGRAM PWSS Schemes of GALSI-I Block under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_1 | ORD/000050/2024-2025 | 767/DWSD | 06/06/2024 | 01/07/2024 | SHUBHRA KANTI GHOSH | 1.12 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block | SM/07869 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Galsi ¿ I Block under Burdwan Division, PHE. Dte._2ND CALL. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000673/2021-2022 | 1738/BWD | 28/03/2022 | 02/04/2025 | JYOTI ENTERPRISE | 5.72 | 0 | 0 | 100
7 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block | SM/07869 | Retrofitting | Acceptance cum Formal Work Order for the work of " Sinking of 300 x 200mm x 150 mtr depth by DR Rig, Repairing & Renovation of existing OHR, Construction of 01 (One) 5.25 x 3.25m No Pump House cum Chlorine Room including laying UPVC distribution system (LDS) and interconnection of PWSS & construction of Boundary wall & other allied works at Golgram under GOLGRAM PWSS, Block- Galsi-I, Dist- Purba Bardhman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II,Assistant Engineer-II (Newly Charge takenover) | Contractual Junior Engineer_1 | ORD/000045/2024-2025 | 771/DWSD | 06/06/2024 | 25/09/2025 | ARISH CONSTRUCTION | 83.56 | 0 | 0 | 90
Total | [13 empty] | 156.81 | 0 | 0