## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mankar Piped Water Supply Scheme at Bagabanpur (Part), Budbud (Part) & Mallikpur (Part) Village (Mouza) under Burwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000098/2021-2022 | 3372/BWD | 23/06/2021 | 22/08/2021 | SAMRAT REALPROJECTS PRIVATE LIMITED | 79.3 | 67.49 | 85.11 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Providing Functional House Hold Tap connection (FHTC) from existing distribution system within the command area of MANKAR piped water supply scheme at Budbud (Part) village Budbud (Part) habitation (Mouza), Galsi-I Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000707/2020-2021 | 547/BWD | 22/01/2021 | 21/02/2021 | SAIKAT RAY | 22.24 | 44.47 | 199.96 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mankar Piped Water Supply Scheme at Sukdal Village (Mouza) 5 nos Habitation under Burwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000110/2021-2022 | 3878/BWD | 27/07/2021 | 25/09/2021 | SUJAY KUMAR RAY | 151.77 | 107.68 | 70.95 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mankar Piped Water Supply Scheme at Mankar (Part) Village (Mouza) under Burwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000097/2021-2022 | 3591/BWD | 13/07/2021 | 11/09/2021 | SAMRAT REALPROJECTS PRIVATE LIMITED | 140.03 | 73.57 | 52.54 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Extension of pipeline in connection with FHTC for MANKAR Piped W/S Scheme under Galsi-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. (Gr.-B) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000085/2021-2022 | 446/DSD | 14/07/2021 | 13/08/2021 | N.B. CONSTRUCTION | 1.81 | 1.78 | 97.98 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC at SUKDAL Village, near Sukdal Petrol and near Hindi School under Mankar (Zone-I) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte._2nd call SL-04 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000530/2022-2023 | 649/DSD | 03/11/2022 | 24/11/2022 | PRATIVA CONSTRUCTION | 4.72 | 4.67 | 98.92 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Retrofitting of RCC Elevated Reservoir (Capacity 450 Cum) by Shortcreting, Guniting etc. in connection with Augmentation of Mankar W/S. Scheme (Zone - I) under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000835/2021-2022 | 6043/BWD | 07/10/2021 | 21/11/2021 | SUDIPTO GORAIN | 19.85 | 19.85 | 99.98 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001045/2021-2022 | 934/DW | 31/01/2022 | 31/01/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001013/2021-2022 |  | 21/01/2022 | 21/01/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Replacement of damaged AC pipeline at Raipur under Mankar (Zone-II) piped water supply scheme within Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-06] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000060/2023-2024 | 182/DSD | 18/04/2023 | 09/05/2023 | MONDAL CONSTRUCTION | 0.97 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Mankar piped water supply scheme at Budbud (Part), Budbud habitation, Malikpara village (Malikpara habitation) & Bagabanpur village (Bagabanpur habitation), Galsi-I Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000518/2020-2021 | 308/BWD | 14/01/2021 | 13/02/2021 | RELIABLE ENGINEERS CO.-OPERATIVE CONSTRUCTION SOCIETY LTD. | 21.83 | 11.63 | 53.29 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Replacement of damage A.C. Pipeline from Mankar Dani Pukur to Purbasa colony via Post Office & Annapurnatala to Panchakalitala under Mankar (Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte._2ND CALL. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000242/2021-2022 | 6633/BWD | 29/11/2021 | 29/12/2021 | PREMANANDA ROY BISWAS | 11.43 | 11.26 | 98.46 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Dismantling of encroachments within Head work site of Mankar (Zone-II) Pipe Water Supply Scheme, at Galsi-I Block within Durgapur(Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [SL-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000545/2021-2022 | 130/DSD | 02/03/2022 | 05/03/2022 | PARTHA RAY | 0.19 | 0 | 0 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Laying of pipe line at North side Canal Bank for construction of diversion road by PWD Dept. under Mankar(Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000627/2021-2022 | 167/DSD | 16/03/2022 | 15/04/2022 | N.B. CONSTRUCTION | 0.65 | 0 | 0 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Connection from newly Retrofitted Over Head Reservoir to Distribution System & Rising main Pipe Line of MANKAR (Zone-I) Water Supply Scheme under Galsi-I Block under within Durgapur Sub Division PHE Dte. Under Burdwan Division PHE Dte. [Gr.-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000272/2022-2023 | 497/DSD | 12/08/2022 | 11/09/2022 | SHUBHRA KANTI GHOSH | 4.77 | 4.52 | 94.78 | 1
16 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Modification to Rising main and D.I. distribution to ensure more controll of water supply of MANKAR water Supply Scheme under Durgapur (Burdwan North) Sub-Division in Galsi-I Block under Burdwan Division, P.H.E. Dte. [SL-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000118/2022-2023 | 336/DSD | 27/06/2022 | 18/07/2022 | SHUBHRA KANTI GHOSH | 2.82 | 2.67 | 94.8 | 1
17 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Replacement of damage A.C. Pipeline at Mankar Bhattacharya Para & New royel club to Battala under Mankar(Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-06 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000532/2022-2023 | 651/DSD | 03/11/2022 | 03/12/2022 | OM ENTERPRISE | 4.72 | 4.68 | 99.17 | 1
18 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC Budbud Village, Girls School Para, Sukanta Nagar etc. under Mankar (Zone-I) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-02 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000528/2022-2023 | 647/DSD | 03/11/2022 | 24/11/2022 | DEY NIRMAN | 4.8 | 4.76 | 99.15 | 1
19 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC near north side of Budbub Canal par colony under Mankar (Zone-I) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-01 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000527/2022-2023 | 646/DSD | 03/11/2022 | 24/11/2022 | ROY CONSTRUCTION | 4.79 | 4.65 | 96.98 | 1
20 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Ground development, vertical extension of valve chamber, construction of pathway, drain etc. at Head work site of Mankar (Z-II) water supply scheme, Block-Galsi-I under Durgapur (Bardhaman North)Sub-Division under Burdwan Division, PHE Dte. SL-05 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000531/2022-2023 | 650/DSD | 03/11/2022 | 03/12/2022 | SAIKAT RAY | 3.42 | 2.98 | 86.99 | 100
21 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Replacement of damage A.C. Pipeline Mankar Pal Para & Nayakpara under Mankar(Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-07 | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000533/2022-2023 | 652/DSD | 03/11/2022 | 03/12/2022 | SOUMYAVASH DAS | 4.55 | 4.41 | 97.07 | 1
22 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) within the command area of Augmentation of MANKAR Piped Water Supply Scheme Near Mankar Masjitala, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-03] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000055/2023-2024 | 178/DSD | 18/04/2023 | 09/05/2023 | SOUMYAVASH DAS | 0.96 | 0.94 | 97.66 | 100
23 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) within the command area of Augmentation of MANKAR Piped Water Supply Scheme at back side of Mankar Girls School, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-04] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000056/2023-2024 | 179/DSD | 18/04/2023 | 09/05/2023 | SHUBHRA KANTI GHOSH | 0.96 | 0.94 | 98.11 | 100
24 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of Augmentation of MANKAR Piped Water Supply Scheme at backside of Mankar Girls School, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-01] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000052/2023-2024 | 176/DSD | 18/04/2023 | 09/05/2023 | SHUBHRA KANTI GHOSH | 0.95 | 0.94 | 98.6 | 95
25 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of MANKAR Piped Water Supply Scheme at Mankar Palpara, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-05] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000025/2023-2024 | 153/DSD | 13/04/2023 | 04/05/2023 | SOUMYAVASH DAS | 0.95 | 0.93 | 98.1 | 100
26 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of Augmentation of MANKAR Piped Water Supply Scheme at Mankar Nayekpara, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-02] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000053/2023-2024 | 177/DSD | 18/04/2023 | 09/05/2023 | SOUMYAVASH DAS | 0.96 | 0.94 | 98.49 | 100
27 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Crossing of Mankar-Guskara Bolgona Road at Head works site of Mankar (Z-I) W/S Scheme for laying distribution and rising main through pushing of 750mm.dia. RCC casing pipe by hydraulic jacking method for Mankar (Z-I) W/S Scheme under Durgapur (Bardhaman North) Sub Division, Burdwan Division, PHE Dte.[SL-12] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000855/2022-2023 | 712/DSD | 30/12/2022 | 29/01/2023 | SHUBHRA KANTI GHOSH | 4.74 | 4.63 | 97.6 | 100
28 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Replacement of damage UPVC Pipeline at Mankar Masjit Tala under Mankar (Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000266/2021-2022 | 693/DSD | 08/12/2021 | 29/12/2021 | SURATH DEY | 1.47 | 1.37 | 93.05 | 1
29 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Shifting of 300 MM dia D.I. pipe and laying of 12 mtr 150 mm dia D.I.pipe for widening of NH2 at Budbud more and supply of 80 mm dia Sluice valve and construction of valve chamber of Mankar Water supply scheme within Galsi -I Block,under Durgapur Sub Division,PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000578/2023-2024 | 658/DSD | 24/08/2023 | 08/09/2023 | SHANKHA GHOSH | 0.96 | 0.96 | 99.56 | 100
30 | PURBA BARDHAMAN |  | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Formal Work Order for Sinking of 300 x 200 mm x 150mtr depth by DR Rig, Construction of 01 (One) no 5.25 x 3.25 m Pump House cum Chlorine room with sanitary arrangement, Boundary wall, including laying UPVC distribution system (LDS) and Providing FHTC and other allied works at Mankar under Retrofitting of Mankar PWSS, Block- Galsi-I, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. (Zone-I/Part-B) | Assistant Engineer-II | Contractual Junior Engineer_1 | ORD/000122/2024-2025 | 1114/DWSD | 02/08/2024 | 30/11/2024 | MANASH GHOSH | 163.89 | 0 | 0 | 0
31 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Laying of new 300 & 200 mm dia sluice valve with valve chamber and replacement of 200 & 150 mm dia sluice valve with valve chamber at Budbud bazar and near NH2 and sukdal within Durgapur Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000568/2023-2024 | 657/DSD | 24/08/2023 | 08/09/2023 | SOUMYAVASH DAS | 0.96 | 0.95 | 98.95 | 100
32 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Laying Parallel pipeline from Mankar Hattala to Bhattacharya para & restore to damage pipeline at difference location of Mallickpara for water supply smoothly of MANKAR (Z-II) and its adjoining mouza's Piped W/S Scheme at Galsi-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. |  |  | ORD/000804/2023-2024 | 4819/BWD | 08/11/2023 | 07/01/2024 | SHUBHRA KANTI GHOSH | 24.08 | 0.38 | 1.6 | 100
33 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Laying of hume pipe 600 MM dia and laying of 48 mtr 315 mm dia HDPE pipe for widening of NH2 crossing at Budbud more fly over of Mankar Water supply scheme within Galsi -I Block,under Durgapur Sub Division,PHE Dte. |  |  | ORD/000987/2023-2024 | 43/DSD | 17/01/2024 | 17/03/2024 | SOUMYAVASH DAS | 4.77 | 4.66 | 97.71 | 100
34 | PURBA BARDHAMAN |  | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Acceptance cum Formal Work Order for the work of Balance Work for Distribution System and Rising Main Pipeline (CV/DVAC/UPVC), Construction of different dia Sluice valve /Air valve/Washout chamber in different sizes, Concrete Road renovation, Mechanical joints for MANKAR (ZONE-II) Water Supply Schemes of GALSI-I Block under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_1 | ORD/000048/2024-2025 | 769/DWSD | 06/06/2024 | 01/07/2024 | SHANKHA GHOSH | 2.06 | 2.06 | 99.75 | 100
35 | PURBA BARDHAMAN |  | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Acceptance cum Formal Work Order for the work of Balance work for Distribution System and Rising Main Pipeline (UPVC/HDPE), Construction of different dia Sluice valve /Air valve/Washout chamber in different sizes,Concrete road renovation for MANKAR (ZONE-I) Water Supply Schemes of GALSI-I Block under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_1 | ORD/000051/2024-2025 | 766/DWSD | 06/06/2024 | 01/07/2024 | SOUMYAVASH DAS | 1.4 | 1.4 | 99.9 | 100
36 | PURBA BARDHAMAN |  | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Acceptance cum Formal Work Order for Drain Constriction & Repairing works For Mankar Water Supply Scheme (Zone-II) at Nayak Para, Dist:- Purba Bardhaman under DWSD, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_1 | ORD/000129/2024-2025 | 1211/DWSD | 23/08/2024 | 02/09/2024 | SOUMYAVASH DAS | 0.66 | 0.65 | 99.48 | 100
37 | PURBA BARDHAMAN |  | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | QUOTATION FOR NEW SERVICE CONNECTION AT MANKAR PWSS ZONE-2 T.W-1 UNDER C.M.D, P.H.E Dte. |  |  | BILL/00263/2024-2025 |  | 31/12/2024 | 31/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.72 | 0 | 0 | 0
38 | PURBA BARDHAMAN |  | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Galsi ¿ I Block under Burdwan Division, PHE. Dte._2ND CALL. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000673/2021-2022 | 1738/BWD | 28/03/2022 | 02/04/2025 | JYOTI ENTERPRISE | 5.72 | 0 | 0 | 100
39 | PURBA BARDHAMAN |  | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Acceptance cum Formal Work Order for the work of "Sinking of 300 X 200mm x 150mtr depth by DR Rig Tube Wells, Construction of 01 (One) no 5.25 x 3.25m Pump House cum Chlorine Room with sanitary arrangement, Boundary Wall including laying UPVC distribution system (LDS) and providing FHTC and allied works at Mankar under Retrofitting of Mankar PWSS (Zone-II, Part-A), under Galsi-I Block, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_1 | ORD/000044/2024-2025 | 760/DWSD | 06/06/2024 | 01/06/2025 | G.S CONSTRUCTION AND CO | 92.69 | 0 | 0 | 10
40 | PURBA BARDHAMAN |  | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | FORMAL WORK ORDER FOR Sinking of 300 x 200 mm x 150 mtr deapth by DR Rig, Construction of 1 (One) no 5.25 x 3.25 m Pump House cum Chlorine room with sanitary arrangement, Boundary wall including laying UPVC distribution system (LDS) and providing FHTC and other allied works at Mankar under Retrofitting of Mankar PWSS, Block- Galsi-I under DURGAPUR W/S DIVISION, PHE DTE. | Assistant Engineer-II | Contractual Junior Engineer_1,JUNIOR ENGINEER-1 | ORD/000266/2024-2025 | 260/DWSD | 11/02/2025 | 05/04/2026 | M/S. GOUTAM ROY | 105.88 | 0 | 0 | 5
41 | PURBA BARDHAMAN |  | Central Mechanical | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1&2 (ZONE:-1&2) at Augmentation MANKAR Water Supply Scheme [ BLOCK- GALSI-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000007/2025-2026 | 1003/CMD | 17/04/2025 | 16/06/2025 | DAS CONSTRUCTION | 51.38 | 0 | 0 | 30
42 | PURBA BARDHAMAN |  | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000027/2024-2025 | 450/DWSD | 17/03/2025 | 17/03/2025 | Resource Division | 0.28 | 0 | 0 | 0
43 | PURBA BARDHAMAN |  | Central Mechanical | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | QUOTATION FOR NEW SERVICE CONNECTION AT MANKAR ZONE-2 T.W-4 UNDER CMD, PHE Dte. |  |  | BILL/00260/2025-2026 | 73 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.29 | 0 | 0 | 0
44 | PURBA BARDHAMAN |  | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | New service connection of Mankar Zone-II PWSS at TW-I |  |  | BILL/00265/2024-2025 | BP-2024-25-117 | 04/02/2025 | 04/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.72 | 0 | 0 | 0
45 | PURBA BARDHAMAN |  | Central Mechanical | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | QUOTATION FOR NEW SERVICE CONNECTION AT MANKAR ZONE-I, T.W-4 UNDER CMD,PHE Dte. |  |  | BILL/00264/2025-2026 | 73 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0 | 0
46 | PURBA BARDHAMAN |  | Central Mechanical | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | QUOTATION FOR NEW SERVICE CONNECTION AT AUG. MANKAR T.W-3 UNDER CMD, PHE Dte. |  |  | BILL/01471/2025-2026 |  | 10/09/2025 | 10/09/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.73 | 0 | 0 | 0
47 | PURBA BARDHAMAN |  | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I | SM/08034 | Retrofitting | Acceptance cum formal Work Order for the work of Sinking of 300 x 200mm x 150mtr depth by DR Rig Tube Well , Construction of 01 (One) no 5.25 x 3.25m Pump House cum Chlorine room with sanitary arrangement, Boundary Wall including laying UPVC distribution system (LDS) and Providing FHTC and other allied works at MANKAR under Retrofitting of Mankar PWSS (Zone-II, Part-B) under Galsi-I Block within Durgapur Water Supply Division P.H.E Dte. | Assistant Engineer-II | Contractual Junior Engineer_1,JUNIOR ENGINEER-1 | ORD/000029/2024-2025 | 757/DWSD | 06/06/2024 | 31/07/2026 | RAMKRISHNA CHAKRABORTY | 66.25 | 9.4 | 14.19 | 60
Total | [13 empty] | 2279.4 | 402.22 | 17.65