## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08705 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000115/2021-2022 | 1103/BWD | 26/02/2022 | 26/02/2022 | Resource Division | 12.3 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08705 | Retrofitting | Acceptance cum Formal Work Order for the work of "Sinking of 300 x 200 mm x 150 mtr deapth by DR, Repairing & Renovation of existing OHR, Construction of 01 (One) no 5.25 x 3.25 m Pump House cum Chlorine Room including laying UPVC distribution system (LDS) and interconnection & other allied works at CHAKTETUL PWSS, Block- Galsi-I, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_1 | ORD/000043/2024-2025 | 759/DWSD | 06/06/2024 | 03/03/2025 | M/S JAYDEEP DASGUPTA | 77.42 | 23.36 | 30.17 | 90
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08705 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of CHAKTENTUL Piped Water Supply Scheme at Chaktentul (1 No Part, 2 Nos Habitation), Bharatpur (2 Nos Habitation) Village (Mouza), Galsi-I Block under Burdwan Division, PHE Dte.(Agreement No. 71/2020-2021 OF SE/CC/PHE. DTE.) | AE(HQs) | J.E. 2 BURDWAN | ORD/000128/2020-2021 | 5005/BWD | 10/12/2020 | 10/03/2021 | SUPRIYA RAY | 75.14 | 25 | 33.27 | 1
4 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08705 | Retrofitting | Quotation for new service connection at Chaktetul Ausgram -I PWSS under CMD/PHED |  |  | BILL/00197/2024-2025 | BP-2024-25-99 | 27/11/2024 | 27/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.38 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08705 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Galsi ¿ I Block under Burdwan Division, PHE. Dte._2ND CALL. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000673/2021-2022 | 1738/BWD | 28/03/2022 | 02/04/2025 | JYOTI ENTERPRISE | 5.72 | 0 | 0 | 100
6 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) | SM/08705 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 446/DWSD | 17/03/2025 | 17/03/2025 | Resource Division | 0.21 | 0 | 0 | 0
Total | [13 empty] | 180.17 | 48.36 | 26.84