## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08708 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of JOTRAGHAB Piped Water Supply Scheme at (JOTKRISHTAI) Mouza under Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000486/2022-2023 | 4007/BWD | 15/09/2022 | 15/10/2022 | PAL CONSTRUCTION | 13.87 | 0 | 0 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08708 | Retrofitting | Quotation for payment of service connection charge on full deposit scheme of Jotraghab w/s scheme. |  |  | VCH/000631/2022-2023 | 724/DW/22-23 | 03/11/2022 | 03/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.76 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08708 | Retrofitting | Quotation for payment of service connection charges for Augmentation of Jotraghab w/s scheme. |  |  | VCH/000632/2022-2023 | 725/DW/22-23 | 03/11/2022 | 03/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.33 | 0 | 0 | 0
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08708 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of JOTRAGHAB Piped Water Supply Scheme at (JOTRAGHAB, RADHABALLAB BATI, KHANPUR, JOTKRISHTAI) Mouza under Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000667/2022-2023 | 382/BWD | 31/01/2023 | 02/03/2023 | KAUSHIK RAY | 21.55 | 0 | 0 | 100
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08708 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of JOTRAGHAB Piped Water Supply Scheme at Jotraghab & Radhaballabbati Mouza), Jamalpur Block under Burdwan Division, PHE. Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. |  | ORD/000058/2022-2023 | 2239/BWD | 02/05/2022 | 16/06/2022 | MAJUMDER ENTERPRISE | 54.07 | 0 | 0 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. | SM/08708 | Retrofitting | Restoration of concrete road ,construction of valve chamber of JOTRAGHAB Piped Water Supply Scheme and its adjoining mouzas within JAMALPUR block under Burdwan Division, PHE Dte. | Assistant Engineer Burdwan Sadar Sub-Division PHE. DTE. | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000850/2023-2024 | 2738/BSD | 28/11/2023 | 28/12/2023 | A R TRADERS | 0.96 | 0 | 0 | 100
Total | [13 empty] | 92.54 | 0 | 0