## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Belari village of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte.[Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000286/2021-2022 | 715/DSD | 17/12/2021 | 01/01/2022 | M/S S. CHOUDHURY | 4.83 | 4.83 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur vilage of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000287/2021-2022 | 716/DSD | 17/12/2021 | 01/01/2022 | M/S S. CHOUDHURY | 4.83 | 4.83 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from distribution system within the command area of KAYRAPUR Water Supply Scheme (Part-A) at Belari, Bara, Bhada & Kayrapur (Part) village under JAL SAPNO MISSION under Ausgram-I Block in Purba Bardhanan District under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000341/2021-2022 | 26/BWD | 04/01/2022 | 03/02/2022 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 42.23 | 42.94 | 101.69 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Belari village of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000480/2021-2022 | 736/DSD | 28/12/2021 | 12/01/2022 | M/S S. CHOUDHURY | 4.83 | 4.83 | 100 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur vilage of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000481/2021-2022 | 737/DSD | 28/12/2021 | 12/01/2022 | M/S S. CHOUDHURY | 4.83 | 4.83 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001237/2021-2022 | 1132/DW | 26/02/2022 | 26/02/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from distribution system within the command area of KAYRAPUR Water Supply Scheme (Part-B) at Billogram, Brajapur, Asinda and Noada village under JAL SAPNO MISSION under Ausgram-I Block in Purba Bardhanan District under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000450/2021-2022 | 860/BWD | 11/02/2022 | 12/04/2022 | ASHOK KUMAR GHOSH | 95.9 | 51.4 | 53.6 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Land development and Construction of connecting road from PH to OHR at 1st tube well site of KAYRAPUR Water Supply Scheme (Part-B) within Durgapur Sub Division Under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000383/2023-2024 | 558/DSD | 20/07/2023 | 19/08/2023 | SAMANTA CONSTRUCTION | 4.84 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Kayrapur Village, Ausgram-I Block within Kayrapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) |  |  | ORD/000730/2023-2024 | 823/AE/HQ | 30/10/2023 | 29/11/2023 | ISHAN CONSTRUCTION | 0.76 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhada village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte.. [SL. No. : 20] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000028/2021-2022 | 3399/BWD | 24/06/2021 | 09/07/2021 | M/S S. CHOUDHURY | 4.86 | 4.86 | 100 | 1
11 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 19] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000029/2021-2022 | 3398/BWD | 24/06/2021 | 09/07/2021 | M/S S. CHOUDHURY | 4.86 | 4.86 | 100 | 1
12 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Laying of rising main in between two number of Tube wells to Over Head Reservoir for Kayrapur water supply scheme (Part-A) within Durgapur Sub-Division in Ausgram-I Block under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000967/2020-2021 | 991/BWD | 04/02/2021 | 06/03/2021 | M/S S. CHOUDHURY | 7.12 | 0 | 0 | 1
13 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Additional cutting of existing concrete pavement between Node J4 to J51 for laying of 300 mm dia D.I distribution in connection with Laying distribution system of Kayrapur Piped Water Supply Scheme at Ausgram-I Block within Durgapur Sub-Division under Burdwan Division, PHE Dte. (Gr.-C) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000965/2020-2021 | 109/DSD | 29/01/2021 | 13/02/2021 | M/S S. CHOUDHURY | 4.05 | 0 | 0 | 1
14 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Koranji village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 21] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000030/2021-2022 | 3397/BWD | 24/06/2021 | 09/07/2021 | M/S S. CHOUDHURY | 3.44 | 3.44 | 100 | 1
15 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Restoration of damaged pipeline of distribution main for construction of drain at Billwagram village within Kayrapur W/S Scheme (Part-B) in Ausgram-I Block under Burdwan Division, P.H.E. Dte.[SL-11] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000035/2023-2024 | 159/DSD | 13/04/2023 | 04/05/2023 | SANDIPAN SENGUPTA | 0.52 | 0.52 | 100 | 100
16 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Relaying and restoration of damaged pipeline of distribution main for construction of drain at Brajapur, Chonary and Asinda village to keep on FHTC within Kayrapur W/S Scheme (Part-B) in Ausgram-I Block under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000562/2023-2024 | 651/DSD | 24/08/2023 | 23/09/2023 | TARAMA AGENCY | 0.95 | 0.95 | 100 | 100
17 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000121/2021-2022 | 1110/BWD | 26/02/2022 | 26/02/2022 | Resource Division | 25.78 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of November'2022. |  |  | BILL/00286/2022-2023 | 954/JJM/22-23 | 13/01/2023 | 13/01/2023 | SUJAUDDIN SEKH | 0.38 | 0 | 0 | 0
19 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 19] | AE(HQs) | J.E. 2 BURDWAN | ORD/000534/2020-2021 | 1459/BWD | 18/02/2021 | 05/03/2021 | M/S S. CHOUDHURY | 4.86 | 9.73 | 200 | 0
20 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Koranji village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 21] | AE(HQs) | J.E. 2 BURDWAN | ORD/000537/2020-2021 | 1457/BWD | 18/02/2021 | 05/03/2021 | M/S S. CHOUDHURY | 4.86 | 9.73 | 200 | 0
21 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhada village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte.. [SL. No. : 20] |  | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000532/2020-2021 | 1458/BWD | 18/02/2021 | 05/03/2021 | M/S S. CHOUDHURY | 4.86 | 9.73 | 200 | 0
22 | PURBA BARDHAMAN |  | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Construction of boundary wall at 2nd Tube well site of KAYRAPUR Water Supply Scheme (Part-B) and its adjoining mouzas, Block-Ausgram-I, under Burdwan Division P.H.E. Dte. |  | Junior Engineer ,Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000988/2023-2024 | 44/DSD | 17/01/2024 | 16/02/2024 | SK BADIUZZAMAL | 3.83 | 0 | 0 | 100
23 | PURBA BARDHAMAN |  | Durgapur W/S Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. | SM/08710 | Retrofitting | Acceptance cum Formal Work Order for Balance work for distribution system HDPE earth work & concrete work for Kayrapur PWSS, Block- Ausgram-I under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_3 | ORD/000131/2024-2025 | 1240/DWSD | 29/08/2024 | 13/09/2024 | TARA MA AGENCY | 1 | 0.47 | 47.3 | 100
Total | [13 empty] | 455.42 | 157.96 | 34.68