## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Repairing and painting of 2 Nos existing Pump House for Kota Chnadipur Pipe Water Supply Scheme, Block- Ausgram-II, under Durgapur Sub-Division, P.H.E Dte. within Burdwan Division P.H.E. Dte. Dist:Purba Bardhaman. [Gr.-E] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000137/2022-2023 | 346/DSD | 30/06/2022 | 14/08/2022 | SUNNY CONSTRUCTION | 2.13 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Route Survey & Preparation of DPR for KOTA-CHANDIPUR PWSS under Ausgram-II under Durgapur (Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-A] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000645/2021-2022 | 99/DSD | 18/02/2022 | 05/03/2022 | SIRCON ENGINEERING SERVICES | 2.74 | 2.74 | 100 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Sinking of additional 250 X 150mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for KOTACHANDIPUR Piped Water Supply Scheme, Block - Ausgram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000033/2022-2023 | 2202/BWD | 28/04/2022 | 28/05/2022 | ANIRUDDHA FARUQUE | 10.15 | 9.57 | 94.31 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. |  |  | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation-1 of Kotachandipur Water Supply Scheme [ Block- Ausgram-I ] at Tube well No.-3 under CMD, PHE Dte., Dist.- Purba-Bardhaman |  |  | ORD/000622/2022-2023 | 2100/CMD | 08/09/2022 | 08/10/2022 | DELTA ENGINEERING ENTERPRISE | 11.65 | 11.4 | 97.8 | 0
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Work Order for Augmentation of Kota-Chandipur Water Supply Scheme with LDS, Rising Main, FHTC work, Pump House & Boundary Wall of Ausgram ¿ II Block in Burdwan (North) Sub-Division, District ¿ Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000310/2021-2022 | 7088/BWD | 22/12/2021 | 21/05/2022 | TIRUPATI ENTERPRISES | 218.89 | 218.04 | 99.61 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000311/2022-2023 | 3624/BWD | 22/08/2022 | 11/09/2022 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 3.69 | 25 | 1
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Construction of drain at new 3rd Tube well site of Augmentation of Kota Chandipur water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, Phe Dte.[SL-03] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000041/2023-2024 | 169/DSD | 18/04/2023 | 09/05/2023 | PARTHA RAY | 0.96 | 0.93 | 97.46 | 100
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Construction of pathway at new 3rd Tube well site of Augmentation of Kota Chandipur water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, Phe. Dte.[SL-05] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000043/2023-2024 | 171/DSD | 18/04/2023 | 09/05/2023 | M/S MUKHERJEE CONSTRUCTION | 0.96 | 0.95 | 99.83 | 100
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Ground development at new 3rd Tube well site of Augmentation of Kota Chandipur water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, Phe. Dte.[SL-04] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000042/2023-2024 | 170/DSD | 18/04/2023 | 09/05/2023 | M/S MUKHERJEE CONSTRUCTION | 0.91 | 0.91 | 99.97 | 100
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Restoration of village Road dismantled by laying pipeline for providing FHTC at Kota Ankure para, Bauripara & Loharpara under Augmentation of KOTA-CHANDIPUR Piped Water Supply Scheme under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-07] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000058/2023-2024 | 181/DSD | 18/04/2023 | 09/05/2023 | PARTHA RAY | 0.96 | 0.95 | 99.11 | 100
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Colour washing, lettering, earthling and other allied works of RCC elevated reservoir (Capacity-200 cum) in connection with Augmentation of Kota-Chandipur water supply scheme within Durgapur (Bardhaman North) Sub-Division, PHE Dte, Block-Ausgram-II under Burdwan Division, PHE Dte. [SL-21] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000865/2022-2023 | 720/DSD | 30/12/2022 | 29/01/2023 | TIRUPATI ENTERPRISES | 1.85 | 1.83 | 99.19 | 100
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Retrofitting of RCC elevated reservoir (Capacity-200 cum) by shotcreting, guinting etc. connection with Augmentation of Kota-Chandipur water supply scheme within Durgapur (Bardhaman North) Sub-Division, PHE Dte, Block-Ausgram-II under Burdwan Division, PHE Dte. [SL-22] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000872/2022-2023 | 721/DSD | 30/12/2022 | 29/01/2023 | P. ENTERPRISE | 2.98 | 2.95 | 99.06 | 100
15 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2021-2022 | 7347/BWD | 30/12/2021 | 30/12/2021 | Resource Division | 6.59 | 0 | 0 | 0
16 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2021-2022 | 558/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 6.51 | 0 | 0 | 0
17 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2021-2022 | 771/BWD | 07/02/2022 | 07/02/2022 | Resource Division | 18.27 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000188/2021-2022 | 1384/BWD | 09/03/2022 | 09/03/2022 | Resource Division | 3.83 | 0 | 0 | 0
19 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000237/2021-2022 | 1561/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
20 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000169/2021-2022 | 1329/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 18.37 | 0 | 0 | 0
21 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Quotation for new connection charges for Augmentation of Kotachandipur w/s scheme under Burdwan Division, PHE Dte. T.W. No.-3 [Application No.-5003543454, dt.-05/12/2022, Ref. ID-503235377] |  |  | BILL/00117/2022-2023 | 916/DW | 30/12/2022 | 30/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.02 | 0 | 0 | 0
22 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09699 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of Augmentation of KOTA-CHANDIPUR Piped Water Supply Scheme [Retrofitting] at Kota (Part), village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. |  |  | ORD/000878/2023-2024 | 5358/BWD | 06/12/2023 | 05/01/2024 | DEBJYOTI GOSWAMI | 9.29 | 8.52 | 91.73 | 100
Total | [13 empty] | 3402.93 | 262.49 | 7.71