## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Retrofitting of RCC Elevated Reservoir (Capacity 450 Cum) by Shortcreting, Guniting etc. in connection with Augmentation of Galsi W/S. Scheme under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000819/2021-2022 | 6042/BWD | 07/10/2021 | 21/11/2021 | SUDIPTO GORAIN | 10 | 10 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2021-2022 | 7346/BWD | 30/12/2021 | 30/12/2021 | Resource Division | 13.73 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at H.W, 2nd and 3rd Tubewell site for GALSI Piped Water Supply Scheme, Block - Galsi ¿ II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [3 Nos. GTW]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000641/2021-2022 | 1622/BWD | 21/03/2022 | 20/05/2022 | AUXILIARY TUBE WELL DRILLERS | 35.56 | 18.65 | 52.44 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Augmentation of GALSI Water Supply Scheme with LDS, Rising Main, FHTC Work, Pump House & Boundary Wall of Galsi - II Block in Durgapur (Burdwan North) Sub-Division, District - Purba Bardhaman under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000385/2021-2022 | 257/BWD | 13/01/2022 | 08/01/2024 | M/S EL-CON | 425.49 | 99.89 | 23.48 | 40
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Route Survey & Preparation of DPR for GALSI PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-D] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000655/2021-2022 | 102/DSD | 18/02/2022 | 05/03/2022 | SIRCON ENGINEERING SERVICES | 2.74 | 2.74 | 100 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000311/2022-2023 | 3624/BWD | 22/08/2022 | 11/09/2022 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 3.69 | 25 | 1
7 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of Galsi Water Supply Scheme [ Block- Galsi-ii ] at pwss-2/3 site, Tube well No.-4 under CMD, PHE Dte., Dist.- Purba-Bardhaman | ASSISTANT ENGINEER |  | ORD/000613/2022-2023 | 2097/CMD | 08/09/2022 | 08/10/2022 | UNIVERSAL ENTERPRISES | 11.07 | 10.79 | 97.51 | 1
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2021-2022 | 554/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 23.26 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000098/2021-2022 | 772/BWD | 07/02/2022 | 07/02/2022 | Resource Division | 43.86 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000185/2021-2022 | 1380/BWD | 09/03/2022 | 09/03/2022 | Resource Division | 3.86 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000235/2021-2022 | 1559/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000167/2021-2022 | 1327/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 55.09 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 4629/BWD | 17/10/2022 | 17/10/2022 | Resource Division | 12.32 | 0 | 0 | 0
14 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Quotation for new connection charges for Augmentation of Galsi w/s scheme under Burdwan Division, PHE Dte. T.W. No.-5 [Application No.-5003534483, dt.-28/11/2022, Ref. ID-503226320] |  |  | BILL/00116/2022-2023 | 915/DW | 30/12/2022 | 30/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.67 | 0 | 0 | 0
15 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. |  |  | VCH/001555/2021-2022 | 1194/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
16 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
17 | PURBA BARDHAMAN |  | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 (SL no.5) at Augumentation of Galsi Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000068/2023-2024 | 2563/CMD | 06/06/2023 | 06/07/2023 | C.M. ENTERPRISE | 10.78 | 0 | 0 | 0
18 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Construction of Toilet (Female) at Durgapur (Burdwan North) Sub Division premises under Augmentation of Galsi piped water supply scheme under Burdwan Division PHE Dte. [SL-08] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000059/2023-2024 | 183/DSD | 18/04/2023 | 09/05/2023 | ANWESHA CONSTRUCTION | 0.91 | 0.89 | 98.4 | 100
19 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Dismantling of concrete road in connection of Laying Distribution Network of Ground Water based Piped Water Supply Scheme for Augmentation of GALSI Piped Water Supply Scheme under Galsi-II in Purba Bardhaman District under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000740/2022-2023 | 1084/BWD | 13/03/2023 | 12/04/2023 | M/S EL-CON | 13.75 | 13.67 | 99.36 | 0
20 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Restoration of damages caused by PHE Dte. at Galsi Gohogram Road between 0.00 Km & 1.50 Km. (NH-2 Junction) from laying of underground pipeline under Asansol Highway Division, PW Roads Dte. |  |  | BILL/00024/2023-2024 | 24/JJM | 18/04/2023 | 18/04/2023 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, P.W.(ROADS) DTE. | 4.56 | 0 | 0 | 0
21 | PURBA BARDHAMAN |  | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | FORMAL WORK ORDER FOR Additional work for laying of extension or laying of paralled pipeline construction of boundary wall providing left out FHTC road restoration work inter connection of tube well with allied work for Augmentation of Galsi PWSS Galsi-II Block, Dist- Purba Bardhaman under DURGAPUR W/S DIVISION, PHE DTE. | Assistant Engineer-II | Contractual Junior Engineer_5,Junior Engineer_3 | ORD/000262/2024-2025 | 533/DWSD | 25/03/2025 | 23/06/2025 | J D CONSTRUCTION | 159.4 | 0 | 0 | 0
22 | PURBA BARDHAMAN |  | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | FORMAL WORK ORDER FOR Additional work for Laying of Extension or Laying of parallel Pipeline, Sinking of Tube Well (5th. TW], Pump House, Providing Leftout FHTC, Road Restoration work, Inter Connection of Tube Well, with allied work for Augmentation of GALSI Piped Water Supply Scheme , Galsi-II Block ,Dist - Purba Bardhaman under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Contractual Junior Engineer_5,Junior Engineer_3 | ORD/000289/2024-2025 | 584/DWSD | 26/03/2025 | 24/06/2025 | GHOSH CONSTRUCTION | 107.93 | 0 | 0 | 0
23 | PURBA BARDHAMAN |  | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Setup New Lab at Galsi with Stacking of departmental materials for ongoing JJM Scheme (Galsi PWSS) under DURGAPUR W/S DIVISION,PHE Dte | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000013/2025-2026 | 665/DWSD | 24/04/2025 | 19/05/2025 | SAIKAT RAY | 10.71 | 0 | 0 | 90
24 | PURBA BARDHAMAN |  | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2024-2025 | 469/DWSD | 17/03/2025 | 17/03/2025 | Resource Division | 0.21 | 0 | 0 | 0
25 | PURBA BARDHAMAN |  | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Functionality improvement by valve operation,cheking the pressure of puipeline, chokage cleaning,ferrul wash and interconnection of pipeline etc. at GALSI PWSS under GALSI-II Block under Durgapur Water Supply Division, PHE Dte. (Sl-08) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer_3 | ORD/000189/2025-2026 | 266/DWSD | 25/02/2026 | 12/03/2026 | SWAPAN KUMAR ROY | 0.99 | 0 | 0 | 0
26 | PURBA BARDHAMAN |  | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at GALSI PWSS under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-I | Junior Engineer_3 | ORD/000245/2026-2027 | 859/DWSD | 25/06/2026 | 25/06/2027 | SWAPAN KUMAR ROY | 5.08 | 0 | 0 | 0
27 | PURBA BARDHAMAN |  | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Repairing of damaged Pipeline at Babla Mouza GALSI PWSS of GALSI block -II under DWSD,PHE Dte, Dte | Assistant Engineer-I | Junior Engineer_3 | ORD/000186/2026-2027 | 723/DWSD | 03/06/2026 | 18/06/2026 | SWAPAN KUMAR ROY | 0.98 | 0 | 0 | 0
28 | PURBA BARDHAMAN |  | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | Repairing of damaged Pipeline (50mm,63mm,75mm,90 mm,110mm & 140mm dia HDPE) GALSI PWSS of GALSI block -II (Galsi- Chowmatha to station road) under DWSD,PHE Dte.(Part-B) | Assistant Engineer-I | Junior Engineer_3 | ORD/000180/2026-2027 | 713/DWSD | 03/06/2026 | 18/06/2026 | SWAPAN KUMAR ROY | 0.96 | 0 | 0 | 0
29 | PURBA BARDHAMAN |  | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09712 | Augmentation | C/O for the work of supply, delivery of different dia CIDF Sluice Valve at Galsi Divisional Store under DWSD ,PHE Dte | Assistant Engineer-I | Junior Engineer_3 | ORD/000196/2026-2027 | 823/DWSD | 23/06/2026 | 08/07/2026 | ISHAAN ENTERPRISE | 6.83 | 0 | 0 | 0
Total | [13 empty] | 4046.63 | 160.32 | 3.96