## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Route Survey & Preparation of DPR for DIGNAGAR PWSS under Durgapur (Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000648/2021-2022 | 100/DSD | 18/02/2022 | 05/03/2022 | SIRCON ENGINEERING SERVICES | 2.81 | 2.81 | 100 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  |  | VCH/001578/2021-2022 | 1207/DW | 10/03/2022 | 10/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Augmentation of DIGNAGAR Piped Water Supply Scheme with LDS, FHTC Work, Rising Main, Switch room (with water supply & sanitary arrangements), 400 cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Boundary wall construction (New TW Site) with repairing of existing switch room cum chlorine room, Block ¿ Ausgram ¿ I, District - Purba Bardhaman. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000410/2021-2022 | 289/BWD | 17/01/2022 | 17/01/2023 | S.S. ENTERPRISE | 390.11 | 388.86 | 99.68 | 1
4 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of DIGNAGAR Piped Water Supply Scheme, Block - Ausgram I, Dist Purba Bardhaman under Burdwan Division, PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000056/2022-2023 | 2234/BWD | 29/04/2022 | 29/05/2022 | J. K. CORPORATION | 14.12 | 12.03 | 85.21 | 1
5 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000311/2022-2023 | 3624/BWD | 22/08/2022 | 11/09/2022 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 3.69 | 25 | 1
6 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Laying of UPVC pipe line by replacement of AC pipe, installation new SSP and Sluice valve, restoration of existing Street Stand Posts, Valve chamber, and allied work of DIGNAGAR W/S Scheme under Durgapur (Burdwan North)Sub Division under Burdwan Division, P.H.E. Dte.[Gr.-F] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000187/2021-2022 | 624/DSD | 25/10/2021 | 09/12/2021 | ANWESHA CONSTRUCTION | 2.08 | 2.04 | 97.88 | 1
7 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2021-2022 | 552/BWD | 27/01/2022 | 27/01/2022 | Resource Division | 12.66 | 0 | 0 | 0
8 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000166/2021-2022 | 1326/BWD | 08/03/2022 | 08/03/2022 | Resource Division | 36.24 | 0 | 0 | 0
9 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000184/2021-2022 | 1379/BWD | 09/03/2022 | 09/03/2022 | Resource Division | 4.45 | 0 | 0 | 0
10 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000064/2021-2022 | 618/BWD | 28/01/2022 | 28/01/2022 | Resource Division | 22.71 | 0 | 0 | 0
11 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000234/2021-2022 | 1558/BWD | 15/03/2022 | 15/03/2022 | Resource Division | 0.37 | 0 | 0 | 0
12 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Quotation for Dignagar water supply scheme. P.H. No.-03 [Quotation Memo No.-5003612925/Quot/03, dt.-17/02/2023] |  |  | BILL/00374/2022-2023 | 1169/JJM | 10/03/2023 | 10/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.06 | 0 | 0 | 0
13 | PURBA BARDHAMAN |  | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Installation of AIR valve with MS pipe Connection near both side of Dignagar irrigation Canal under Augmentation of DIGNAGAR and its adjoining mouza¿s piped W/S Scheme at Ausgram-I Block within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000940/2023-2024 | 912/DSD | 15/12/2023 | 14/01/2024 | S.S. ENTERPRISE | 0.96 | 0.91 | 94.32 | 100
14 | PURBA BARDHAMAN |  | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Acceptance cum formal work order for the work of " Supplying & Laying of different dia UPVC pipe at Dignagar under Dignagar PWSS, Block- Aushgram-I, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_4 | ORD/000037/2024-2025 | 761/DWSD | 06/06/2024 | 21/02/2025 | SAFTI PRIVATE LIMITED | 53.8 | 0 | 0 | 35
15 | PURBA BARDHAMAN |  | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. | SM/09713 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2024-2025 | 465/DWSD | 17/03/2025 | 17/03/2025 | Resource Division | 0.14 | 0 | 0 | 0
Total | [13 empty] | 3562.27 | 410.33 | 11.52