## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN | SM/10055 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of augmentation BHALKI Piped Water Supply Scheme at Bhalki (Part), Chandipur (Part), Samantapara (Part), Telota (Part) & Abhirampuri (Part) village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000006/2022-2023 | 1907/BWD | 07/04/2022 | 07/05/2022 | ROY CONSTRUCTION | 49.52 | 49.18 | 99.32 | 1
2 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN | SM/10055 | Retrofitting | Construction of Drain and restoration of connection for Augmentation of BHALKI W/S Scheme , Block- Ausgram-II, under Durgapur (Burdwan North)Sub Division Burdwan Division, P.H.E. Dte. [SL-B] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000121/2022-2023 | 334/DSD | 27/06/2022 | 27/07/2022 | TAUSIF HOSSAIN MONDAL | 1.88 | 0 | 0 | 1
3 | PURBA BARDHAMAN |  | Burdwan Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN | SM/10055 | Retrofitting | Making structure with GI pipe for provision of joining and laying of pipeline near Abhirampur branch Canal for Bhalki and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-H] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000134/2022-2023 | 349/DSD | 30/06/2022 | 14/08/2022 | PARTHA RAY | 1.9 | 0 | 0 | 1
4 | PURBA BARDHAMAN |  | Durgapur W/S Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN | SM/10055 | Retrofitting | Acceptance cum Formal Work Order for the work of Sinking of 250 x 150 mtr deapth by DR Rig and supplying and laying of UPVC pipe line (LDS) and construction of temporary KIOSK for arrangement of electrification of Tube well at BHALKI under BHALKI PWSS , Block- Ausgram-II, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_5 | ORD/000055/2024-2025 | 772/DWSD | 06/06/2024 | 04/09/2024 | EVEREST INFRATECH INC | 64.56 | 0 | 0 | 0
Total | [13 empty] | 117.86 | 49.18 | 41.73