## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 3.99 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Material Requisition To Resource Division |  |  | RTOR000256/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 18.44 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Material Requisition To Resource Division |  |  | RTOR000495/2023-2024 | 4019/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 4.01 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Material Requisition To Resource Division |  |  | RTOR000642/2023-2024 | 5108/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 20.18 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 25/12/2024 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 1724/C/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 3.52 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Quotation for new service connection at Bhota W/S Scheme for PH No-2 |  |  | BILL/01822/2023-2024 | BP-2023-24-326 | 03/01/2024 | 03/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.81 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Quotation for new service connection at Bhota W/S Scheme for PH No-1 |  |  | BILL/01823/2023-2024 | BP-2023-24-325 | 03/01/2024 | 03/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.77 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AUSGRAM & BHOTA Piped Water Supply Scheme under Ausgram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000430/2023-2024 | 3324/BWD | 02/08/2023 | 16/09/2025 | DUTTA ENTERPRISE | 763.14 | 96.65 | 12.67 | 70
10 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bhota Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000741/2023-2024 | 4051/CMD | 29/08/2023 | 05/05/2025 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 29.56 | 11.77 | 39.81 | 48
11 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Material Requisition To Resource Division |  |  | RTOR000032/2024-2025 | 452/DWSD | 17/03/2025 | 17/03/2025 | Resource Division | 0.14 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | BHOTA PIPED WATER SUPPLY SCHEME | SM/13293 | New | Acceptance cum Formal Work Order for LDS,FHTC,Road Restoration,Develop Boundary Wall Hight & Land Developement making With necessary allied works at AUSGRAM-I Block of BHOTA PWSS under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_1,JUNIOR ENGINEER-1 | ORD/000180/2024-2025 | 1617/DWSD | 26/11/2024 | 24/05/2026 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 55.22 | 0 | 0 | 40
Total | [13 empty] | 958.33 | 108.42 | 11.31