## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | Material Requisition To Resource Division |  |  | RTOR000078/2022-2023 | 1255/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 8.72 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 1629/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 0.41 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | Material Requisition To Resource Division |  |  | RTOR000635/2023-2024 | 5091/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 21.7 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | New service connection charges for Sonaiaima PWSS TW-2 |  |  | BILL/00775/2023-2024 | BP-2023-24-99 | 02/08/2023 | 02/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.06 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | New service connection charges for Sonaiaima PWSS TW-1 |  |  | BILL/00720/2023-2024 | BP-2023-24-46 | 13/07/2023 | 13/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.13 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sonaiaima Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000041/2023-2024 | 2493/CMD | 01/06/2023 | 01/07/2023 | CHATTERJEE ENTERPRISE | 27.71 | 0 | 0 | 40
7 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | Material Requisition To Resource Division |  |  | RTOR000017/2024-2025 | 1724/B/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 7.42 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | FOMAL WORK ORDER FOR Balance works related (Sinking of Tube Wells at Bilaspur Village, LDS, Rising Mains, FHTCs, Road restoration of Sonaiaima PWSS under Ausgram-II Block under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_2 | ORD/000221/2024-2025 | 128/DWSD | 22/01/2025 | 22/05/2025 | RANADHIR SINHA | 131.08 | 0 | 0 | 30
9 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | SONAIAIMA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under AUSGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | JUNIOR ENGINEER BURDWAN SADAR SUB-DIVISION PHE DTE | ORD/000639/2022-2023 | 254/BWD | 16/01/2023 | 01/04/2025 | RANADHIR SINHA | 360.13 | 0 | 0 | 100
10 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | Ground development at Head Work site of SONAIAIMA Piped water supply Scheme, block ¿ Ausgram - I within Durgapur Sub Division under Burdwan Division P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000676/2023-2024 | 723/DSD | 21/09/2023 | 21/10/2023 | SINHA BROTHERS | 0.94 | 0 | 0 | 100
11 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | Repairing and restore pipe line damaged by newly laying of pipeline at different location of Somai village (West Part) SONAIAIMA and its adjoining mouza's Piped W/S Scheme (NEW) at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000675/2023-2024 | 722/DSD | 21/09/2023 | 06/10/2023 | RANADHIR SINHA | 0.87 | 0 | 0 | 100
12 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme | SM/13326 | New | Repairing and restore pipe line damaged by newly laying of pipeline at different location of Somai village ( East Part) SONAIAIMA and its adjoining mouza's Piped W/S Scheme (NEW) at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000673/2023-2024 | 721/DSD | 21/09/2023 | 06/10/2023 | RANADHIR SINHA | 0.86 | 0 | 0 | 100
Total | [13 empty] | 572.02 | 0 | 0