## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Material Requisition To Resource Division |  |  | RTOR000095/2022-2023 | 1644/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 43.68 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 1268/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 16.43 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Material Requisition To Resource Division |  |  | RTOR000639/2023-2024 | 5105/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 24.22 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | New service connection charges of Chhora PWSS TW-2 |  |  | BILL/00747/2023-2024 | BP-2023-24-47 | 13/07/2023 | 13/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.44 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | New service connection charges of Chhora PWSS TW-1 |  |  | BILL/00746/2023-2024 | BP-2023-24-48 | 13/07/2023 | 13/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.21 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Acceptance cum Formal Work Order for Sinking of 300 X 200mm dia Tube Well- 300 mtr.& 2 nos Trial Bore of 200 X 200mm dia Tube Well- 300 mtr at Pubar village under Chhora PWSS (JJM) Block - Ausgram -II, District:- Purba-Bardhaman, under Durgapur W/S Division , PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000169/2024-2025 | 1612/DWSD | 26/11/2024 | 25/01/2025 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 34.01 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-II under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.03.2024 to 31.08.2024 (6 Months)(Sl-02) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000295/2023-2024 | 268/DWSD | 29/02/2024 | 06/03/2024 | PRAMIT CHATTERJEE | 0.82 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHHORA Water Supply Scheme [ Block- AUSGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000054/2023-2024 | 2514/CMD | 02/06/2023 | 02/07/2023 | MITRA ENTERPRISE | 29.43 | 0 | 0 | 45
9 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Acceptance cum Formal Work Order work of Balance work for renovation and modification of administrative office building at PHE Complex 2nd Floor, Nababhat, P.O- Fagupur, Dist- Purba Bardhaman inconnection with Augmentation of Chhora PWSS under Aushgram-II Block. | Assistant Engineer-I | JUNIOR ENGINEER-2 | ORD/000301/2023-2024 | 364/DWSD | 15/03/2024 | 14/04/2024 | SANDIPAN SENGUPTA | 9.6 | 0 | 0 | 100
10 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 1724/H/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 7.83 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-II under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.09.2024 to 28.02.2025 (6 Months)(Sl-02) | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000139/2024-2025 | 1249/DWSD | 30/08/2024 | 28/02/2025 | PRAMIT CHATTERJEE | 0.82 | 0 | 0 | 20
12 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2025 to 31.05.2025 (3 Months). | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000281/2024-2025 | 341/DWSD | 27/02/2025 | 27/05/2025 | PRAMIT CHATTERJEE | 0.41 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Contractual Junior Engineer_1,Contractual Junior Engineer_2,Contractual Junior Engineer_3,Contractual Junior Engineer_4,Contractual Junior Engineer_5,JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 20/09/2025 | MANASH GHOSH | 745.87 | 0 | 0 | 1
14 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.06.2025 to 31.08.2025 (3 Months). | Assistangt Engineer,Assistant Engineer-II,Assistant Engineer-II (Newly Charge takenover) | JUNIOR ENGINEER-2 | ORD/000042/2025-2026 | 854/DWSD | 29/05/2025 | 27/08/2025 | PRAMIT CHATTERJEE | 0.41 | 0 | 0 | 0
15 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | CHHORA PIPED WATER SUPPLY SCHEME | SM/13328 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KHANDARI & CHHORA Piped Water Supply Scheme under Ausgram II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000735/2022-2023 | 1005/BWD | 06/03/2023 | 30/01/2025 | M/S NATIONAL CONSTRUCTION | 1331.54 | 0 | 0 | 100
Total | [13 empty] | 2256.74 | 0 | 0