## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram - I | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME | SM/13330 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1962/BWD | 25/04/2023 |  | Resource Division | 25.71 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram - I | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME | SM/13330 | New | Material Requisition To Resource Division |  |  | RTOR000189/2023-2024 | 2155/BWD | 10/05/2023 |  | Resource Division | 11.16 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram - I | Central Mechanical | PICHKURI PIPED WATER SUPPLY SCHEME | SM/13330 | New | New service connection charges for Pichkuri PWSS TW-1 |  |  | BILL/00762/2023-2024 | BP-2023-24-64 | 18/07/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.96 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram - I | Central Mechanical | PICHKURI PIPED WATER SUPPLY SCHEME | SM/13330 | New | New service connection charges for Pichkuri PWSS TW-2 |  |  | BILL/00763/2023-2024 | BP-2023-24-65 | 18/07/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.26 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram - I | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME | SM/13330 | New | Material Requisition To Resource Division |  |  | RTOR000602/2023-2024 | 4908/BWD | 10/11/2023 |  | Resource Division | 12.03 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram - I | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME | SM/13330 | New | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001180/2023-2024 | 995/DSD | 29/12/2023 | 29/06/2024 | SUJAUDDIN SEKH | 2 | 0 | 0 | 60
7 | PURBA BARDHAMAN | Ausgram - I | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME | SM/13330 | New | PICHKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000064/2023-2024 | 1985/BWD | 27/04/2023 | 26/04/2024 | BANSBERIA CONSTRUCTION CO. | 445.01 | 233.77 | 52.53 | 90
8 | PURBA BARDHAMAN | Ausgram - I | Central Mechanical | PICHKURI PIPED WATER SUPPLY SCHEME | SM/13330 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Pichkuri Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000150/2023-2024 | 2886/CMD | 10/07/2023 | 09/08/2023 | CHATTERJEE ENTERPRISE | 27.75 | 11.08 | 39.92 | 98
9 | PURBA BARDHAMAN | Ausgram - I | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME | SM/13330 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/06/2024 to 31/07/2024) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000184/2024-2025 | 411/DSD | 28/05/2024 | 28/07/2024 | SUJAUDDIN SEKH | 0.8 | 0.76 | 94.54 | 0
Total | [13 empty] | 530.68 | 245.61 | 46.28