## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 1267/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 13.39 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 65.98 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | Material Requisition To Resource Division |  |  | RTOR000378/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 16.58 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | Material Requisition To Resource Division |  |  | RTOR000636/2023-2024 | 5104/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 21.42 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | New service connection charges for Khandari PWSS TW 2 |  |  | BILL/00816/2023-2024 | BP-2023-24-98 | 02/08/2023 | 02/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.97 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | New service connection charges for Khandari PWSS TW-1 |  |  | BILL/00721/2023-2024 | BP-2023-24-49 | 13/07/2023 | 13/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.71 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khandari Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000045/2023-2024 | 2508/CMD | 02/06/2023 | 02/07/2023 | CHOUDHURY ENTERPRISE | 27.79 | 22.62 | 81.41 | 98
8 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 1724/J/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 11.03 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Contractual Junior Engineer_1,Contractual Junior Engineer_2,Contractual Junior Engineer_3,Contractual Junior Engineer_4,Contractual Junior Engineer_5,JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 20/09/2025 | MANASH GHOSH | 745.87 | 0 | 0 | 1
10 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KHANDARI & CHHORA Piped Water Supply Scheme under Ausgram II Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000735/2022-2023 | 1005/BWD | 06/03/2023 | 30/01/2025 | M/S NATIONAL CONSTRUCTION | 1331.54 | 642.9 | 48.28 | 100
11 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 449/DWSD | 17/03/2025 | 17/03/2025 | Resource Division | 0.14 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | KHANDARI PIPED WATER SUPPLY SCHEME | SM/13396 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 80
Total | [13 empty] | 2334.7 | 665.53 | 28.51