## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | Karatia Piped Water Supply Scheme | SM/13397 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 4.22 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | Karatia Piped Water Supply Scheme | SM/13397 | New | Material Requisition To Resource Division |  |  | RTOR000315/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 13.44 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | Karatia Piped Water Supply Scheme | SM/13397 | New | Material Requisition To Resource Division |  |  | RTOR000633/2023-2024 | 4875/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 25.7 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | Karatia Piped Water Supply Scheme | SM/13397 | New | New service connection charges for Karatia PWSS TW-2 |  |  | BILL/01465/2023-2024 | BP-2023-24-161 | 18/09/2023 | 18/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.19 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | Karatia Piped Water Supply Scheme | SM/13397 | New | New service connection charges for Karatia PWSS TW-1 |  |  | BILL/00961/2023-2024 | BP-2023-24-117 | 16/08/2023 | 16/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.9 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | Karatia Piped Water Supply Scheme | SM/13397 | New | Continuation work for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-II) on hire basis for the office of the assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE.Govt. of West Bengal (for the period of December'2023 to May'2024) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte |  | ORD/000971/2023-2024 | 877/DSD | 30/11/2023 | 31/05/2024 | SUJAUDDIN SEKH | 0.87 | 0 | 0 | 50
7 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | Karatia Piped Water Supply Scheme | SM/13397 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/06/2024 to 31/07/2024) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000184/2024-2025 | 411/DSD | 28/05/2024 | 28/07/2024 | SUJAUDDIN SEKH | 0.8 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | Karatia Piped Water Supply Scheme | SM/13397 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 25/12/2024 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | Karatia Piped Water Supply Scheme | SM/13397 | New | KARATIA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000368/2023-2024 | 3082/BWD | 18/07/2023 | 01/01/2026 | BANSBERIA CONSTRUCTION CO. | 578.76 | 0 | 0 | 95
10 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | Karatia Piped Water Supply Scheme | SM/13397 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Contractual Junior Engineer_1,Contractual Junior Engineer_2,Contractual Junior Engineer_3,Contractual Junior Engineer_4,Contractual Junior Engineer_5,JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 20/09/2025 | MANASH GHOSH | 745.87 | 0 | 0 | 1
11 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | Karatia Piped Water Supply Scheme | SM/13397 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Karatia Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000233/2023-2024 | 3172/CMD | 26/07/2023 | 25/08/2023 | C.M. ENTERPRISE | 27.12 | 0 | 0 | 96
Total | [13 empty] | 1457.43 | 0 | 0