## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME | SM/13466 | New | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 1266/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 3.1 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME | SM/13466 | New | Material Requisition To Resource Division |  |  | RTOR000097/2022-2023 | 1635/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 16.63 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME | SM/13466 | New | Material Requisition To Resource Division |  |  | RTOR000593/2023-2024 | 4901/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 34.12 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME | SM/13466 | New | New service connection charges for Chak Radhamohanpur PWSS TW-1 |  |  | BILL/00759/2023-2024 | BP-2023-24-59 | 17/07/2023 | 17/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.13 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME | SM/13466 | New | New service connection charges for Chak Radhamohanpur PWSS TW-2 |  |  | BILL/00764/2023-2024 | BP-2023-24-62 | 18/07/2023 | 18/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.09 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME | SM/13466 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chak Radhamohanpur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000040/2023-2024 | 2492/CMD | 01/06/2023 | 01/07/2023 | MS DAS ELECTRIC CO | 27.73 | 22.32 | 80.5 | 40
7 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME | SM/13466 | New | Addl. Quotation for new electric service connection at Chak Radhamohanpur PH NO.-2 |  |  | BILL/01757/2023-2024 | BP-2023-24-265 | 11/12/2023 | 11/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.76 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME | SM/13466 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 80
9 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME | SM/13466 | New | CHAK RADHAMOHANPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000677/2022-2023 | 453/BWD | 06/02/2023 | 04/10/2023 | HAMID SK | 122.63 | 122.56 | 99.95 | 100
Total | [13 empty] | 309.46 | 144.89 | 46.82