## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Satinandi Water Supply Scheme [ Block- Galsi-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000044/2023-2024 | 2496/CMD | 01/06/2023 | 01/07/2023 | DEY ENTERPRISE | 27.74 | 20.12 | 72.52 | 50
2 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 1264/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 8.15 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Material Requisition To Resource Division |  |  | RTOR000497/2023-2024 | 4021/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.24 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Material Requisition To Resource Division |  |  | RTOR000600/2023-2024 | 4906/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 33.07 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | New service connection charges of Satinandi Water Supply Scheme TW-2 |  |  | BILL/00675/2023-2024 | BP-2023-24-26 | 21/06/2023 | 21/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.05 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | New service connection charges of Satinandi Water Supply Scheme TW-1 |  |  | BILL/00674/2023-2024 | BP-2023-24-25 | 21/06/2023 | 21/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.08 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | SATINANDI Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000584/2022-2023 | 5520/BWD | 23/12/2022 | 23/12/2023 | MD HASIN | 389.47 | 389.47 | 100 | 40
9 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 1724/A/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 0.31 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Acceptance cum Formal Work Order for SATINANDI Piped Water Supply Scheme with INSTALLATION OF BARBED WIRE, FHTC ,Road restoration ,DEMOLITION WORK & land development with road at TW site under Galsi-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_4,Junior Engineer_3 | ORD/000183/2024-2025 | 1620/DWSD | 26/11/2024 | 18/10/2025 | A K SIKDAR | 79.05 | 0 | 0 | 70
11 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Acceptance cum Formal Work Order for Sinking of 300 x 200 mm dia tube well 150 mtr depth by DR Rig method for trial bore at Tetulmari & Golgram under Satinandi PWSS (JJM), Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000185/2024-2025 | 1596/DWSD | 25/11/2024 | 15/12/2024 | S & P ENTERPRISE | 7.5 | 0 | 0 | 60
12 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Material Requisition To Resource Division |  |  | RTOR000041/2024-2025 | 461/DWSD | 17/03/2025 | 17/03/2025 | Resource Division | 0.14 | 0 | 0 | 0
Total | [13 empty] | 645.22 | 409.59 | 63.48