## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi - II | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 1264/BWD | 17/03/2023 |  | Resource Division | 8.15 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Galsi - II | Central Mechanical | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | New service connection charges of Satinandi Water Supply Scheme TW-1 |  |  | BILL/00674/2023-2024 | BP-2023-24-25 | 21/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.08 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi - II | Central Mechanical | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | New service connection charges of Satinandi Water Supply Scheme TW-2 |  |  | BILL/00675/2023-2024 | BP-2023-24-26 | 21/06/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.05 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi - II | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Material Requisition To Resource Division |  |  | RTOR000497/2023-2024 | 4021/BWD | 08/09/2023 |  | Resource Division | 1.24 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Galsi - II | Central Mechanical | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Satinandi Water Supply Scheme [ Block- Galsi-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000044/2023-2024 | 2496/CMD | 01/06/2023 | 01/07/2023 | DEY ENTERPRISE | 27.74 | 20.12 | 72.52 | 50
6 | PURBA BARDHAMAN | Galsi - II | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | Material Requisition To Resource Division |  |  | RTOR000600/2023-2024 | 4906/BWD | 10/11/2023 |  | Resource Division | 33.07 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Galsi - II | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME | SM/13494 | New | SATINANDI Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000584/2022-2023 | 5520/BWD | 23/12/2022 | 23/12/2023 | MD HASIN | 389.47 | 270.81 | 69.53 | 40
Total | [13 empty] | 469.8 | 290.93 | 61.92