## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BAHADURPUR PIPED WATER SUPPLY SCHEME | SM/13504 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 0.44 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BAHADURPUR PIPED WATER SUPPLY SCHEME | SM/13504 | New | Material Requisition To Resource Division |  |  | RTOR000217/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 13.54 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BAHADURPUR PIPED WATER SUPPLY SCHEME | SM/13504 | New | Material Requisition To Resource Division |  |  | RTOR000613/2023-2024 | 4916/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 30.36 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | BAHADURPUR PIPED WATER SUPPLY SCHEME | SM/13504 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bahadurpur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000912/2023-2024 | 4176/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 28.59 | 22.35 | 78.16 | 96
5 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BAHADURPUR PIPED WATER SUPPLY SCHEME | SM/13504 | New | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/001180/2023-2024 | 995/DSD | 29/12/2023 | 29/06/2024 | SUJAUDDIN SEKH | 2 | 0.19 | 9.69 | 60
6 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BAHADURPUR PIPED WATER SUPPLY SCHEME | SM/13504 | New | BAHADURPUR Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000464/2023-2024 | 3455/BWD | 08/08/2023 | 04/02/2024 | KOUSIK MALLICK | 190.29 | 190.08 | 99.89 | 95
7 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | BAHADURPUR PIPED WATER SUPPLY SCHEME | SM/13504 | New | NEW SERVICE CONNECTION FOR BAHADURPUR PWSS |  |  | BILL/02471/2023-2024 | BP-2023-24-533 | 13/02/2024 | 13/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.83 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | BAHADURPUR PIPED WATER SUPPLY SCHEME | SM/13504 | New | New service connection for Bahadurpur PWSS |  |  | BILL/02466/2023-2024 | BP-2023-24-529 | 13/02/2024 | 13/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.96 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | BAHADURPUR PIPED WATER SUPPLY SCHEME | SM/13504 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 80
Total | [13 empty] | 372.27 | 212.62 | 57.12