## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 55.76 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | Material Requisition To Resource Division |  |  | RTOR000245/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 12.65 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | Material Requisition To Resource Division |  |  | RTOR000587/2023-2024 | 4944/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 34.27 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | Material Requisition To Resource Division |  |  | RTOR000449/2023-2024 | 3973/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 29.28 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 25/12/2024 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 1724/O/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 4.05 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | NEW SERVICE CONNECTION FOR DIGHA PWSS PH-1. |  |  | BILL/03138/2023-2024 | BP-2023-24-648 | 20/03/2024 | 20/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.12 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | NEW SERVICE CONNECTION FOR DIGHA PWSS |  |  | BILL/02588/2023-2024 | BP-2023-24-554 | 20/02/2024 | 20/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.08 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways at different TW sites for DIGHA Piped Water Supply Scheme under Ausgram-I Block, District:- Purba Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000463/2023-2024 | 3454/BWD | 08/08/2023 | 07/08/2025 | APORUPA CONSTRUCTION | 423.95 | 340.07 | 80.21 | 75
10 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | Formal Work Order for Balance works related sinking of tubewells at GANGARAMPUR village, LDS with Jack Pushing, Rising Main Construction Switchroom and FHTC of DIGHA PWSS of Ausgram-I Block, under Durgapur W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Contractual Junior Engineer_3 | ORD/000179/2024-2025 | 1573/DWSD | 21/11/2024 | 21/03/2025 | MANASH GHOSH | 189.93 | 0 | 0 | 95
11 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | Material Requisition To Resource Division |  |  | RTOR000061/2024-2025 | 481/DWSD | 17/03/2025 | 17/03/2025 | Resource Division | 0.14 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | WBSEDCL QUOTATION FOR DIGHA PWSS PH-3 ,GOLIGRAM , GANGARAMPUR |  |  | BILL/00231/2025-2026 | 73 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 14.36 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | DIGHA PIPED WATER SUPPLY SCHEME | SM/13938 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DIGHA Water Supply Scheme [ Block- AUSGRAM-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000808/2023-2024 | 4093/CMD | 29/08/2023 | 28/09/2023 | A.S. ENTERPRISE | 29.55 | 23.41 | 79.21 | 48
Total | [13 empty] | 855.71 | 363.48 | 42.48