## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-I,Mangolkote | Central Mechanical | KALYANPUR PIPED WATER SUPPLY SCHEME | SM/13939 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kalyanpur Water Supply Scheme [ Block-Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000745/2023-2024 | 4055/CMD | 29/08/2023 | 28/09/2023 | T.N. BANERJEE | 27.71 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-I,Mangolkote | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME | SM/13939 | New | Material Requisition To Resource Division |  |  | RTOR000026/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 25.59 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-I,Mangolkote | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME | SM/13939 | New | Material Requisition To Resource Division |  |  | RTOR000302/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 8.13 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-I,Mangolkote | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME | SM/13939 | New | Material Requisition To Resource Division |  |  | RTOR000588/2023-2024 | 4945/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 34.27 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-I,Mangolkote | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME | SM/13939 | New | Material Requisition To Resource Division |  |  | RTOR000550/2023-2024 | 4313/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 24.08 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-I,Mangolkote | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME | SM/13939 | New | Material Requisition To Resource Division |  |  | RTOR000775/2023-2024 | 201/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 5.46 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-I,Mangolkote | Central Mechanical | KALYANPUR PIPED WATER SUPPLY SCHEME | SM/13939 | New | NEW SERVICE CONNECTION FOR KALYANPUR PWSS. |  |  | BILL/02589/2023-2024 | BP-2023-24-555 | 20/02/2024 | 20/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.16 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-I,Mangolkote | Central Mechanical | KALYANPUR PIPED WATER SUPPLY SCHEME | SM/13939 | New | QUOTATION FOR NEW SERVICE CONNECTION FOR KALYANPUR PWSS PH-2. |  |  | BILL/00194/2024-2025 | BP-2024-25-90 | 17/05/2024 | 17/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.89 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-I,Mangolkote | Central Mechanical | KALYANPUR PIPED WATER SUPPLY SCHEME | SM/13939 | New | Quotation for New service connection for Kalyanpur PWSS PH 1 |  |  | BILL/00249/2024-2025 | BP-2024-25-130 | 05/06/2024 | 05/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.51 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ausgram-I,Mangolkote | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME | SM/13939 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | AE(HQs) | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000727/2023-2024 | 4581/BWD | 16/10/2023 | 07/06/2026 | SAFECO ENTERPRISES | 1551.98 | 0 | 0 | 60
Total | [13 empty] | 1693.79 | 0 | 0