## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | JADABGANJ PIPED WATER SUPPLY SCHEME | SM/13966 | New | Material Requisition To Resource Division |  |  | RTOR000285/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 13.54 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | JADABGANJ PIPED WATER SUPPLY SCHEME | SM/13966 | New | Material Requisition To Resource Division |  |  | RTOR000579/2023-2024 | 4927/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 36.98 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | JADABGANJ PIPED WATER SUPPLY SCHEME | SM/13966 | New | Material Requisition To Resource Division |  |  | RTOR000552/2023-2024 | 4285/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 47.1 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | JADABGANJ PIPED WATER SUPPLY SCHEME | SM/13966 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 25/12/2024 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | JADABGANJ PIPED WATER SUPPLY SCHEME | SM/13966 | New | Continution Work Order for Demarcation of new land of PHE site under various places (Jadabganj PWSS) under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000143/2024-2025 | 1312/DWSD | 12/09/2024 | 27/09/2024 | SAIKAT RAY | 28.57 | 0 | 0 | 70
6 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | JADABGANJ PIPED WATER SUPPLY SCHEME | SM/13966 | New | Acceptance cum Formal Work Order for Demarcation of new land of PHE site under various places (Jadabganj PWSS) under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000133/2024-2025 | 1243/DWSD | 29/08/2024 | 28/09/2024 | SAIKAT RAY | 28.57 | 28.57 | 100 | 80
7 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | JADABGANJ PIPED WATER SUPPLY SCHEME | SM/13966 | New | New service connection at Jadabganj PWSS PH-1 |  |  | BILL/02313/2023-2024 | BP-2023-24-432 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.24 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | JADABGANJ PIPED WATER SUPPLY SCHEME | SM/13966 | New | QUOTATION FOR NEW SERVICE CONNECTION AT JADABGANJ PWSS TW-2 |  |  | BILL/00370/2024-2025 | BP-2024-25-191 | 08/07/2024 | 08/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | JADABGANJ PIPED WATER SUPPLY SCHEME | SM/13966 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | AE(HQs) | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000727/2023-2024 | 4581/BWD | 16/10/2023 | 07/06/2026 | SAFECO ENTERPRISES | 1551.98 | 107.87 | 6.95 | 60
10 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | JADABGANJ PIPED WATER SUPPLY SCHEME | SM/13966 | New | Continution Work Order for Repairing and Renovation of Existing Room for prepair of Laboratory Room and Store Room , Boundary Wall with Gate, side drain with necessary allied works at Galsi-II Head Works site under Jadabganj Pipe Water Supply Scheme (JJM) under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000144/2024-2025 | 1348/DWSD | 20/09/2024 | 18/01/2026 | SAIKAT RAY | 25.7 | 0 | 0 | 95
11 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | JADABGANJ PIPED WATER SUPPLY SCHEME | SM/13966 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Jadabganj Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000767/2023-2024 | 4065/CMD | 29/08/2023 | 10/05/2025 | M/S. SWAPAN BANERJEE | 27.78 | 0 | 0 | 96
Total | [13 empty] | 1826.73 | 136.44 | 7.47