## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | DHARALA PIPED WATER SUPPLY SCHEME | SM/14056 | New | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 1641/BWD | 06/04/2023 | 06/04/2023 | Resource Division | 0.78 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | DHARALA PIPED WATER SUPPLY SCHEME | SM/14056 | New | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 1240/BWD | 17/03/2023 | 17/03/2023 | Resource Division | 2.49 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | DHARALA PIPED WATER SUPPLY SCHEME | SM/14056 | New | Material Requisition To Resource Division |  |  | RTOR000756/2023-2024 | 5243/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 18.5 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | DHARALA PIPED WATER SUPPLY SCHEME | SM/14056 | New | New service connection charges for Dharala PWSS TW-1 |  |  | BILL/00766/2023-2024 | BP-2023-24-68 | 20/07/2023 | 20/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.76 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | DHARALA PIPED WATER SUPPLY SCHEME | SM/14056 | New | DHARALA [DHARALA VILLAGE] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000755/2022-2023 | 1208/BWD | 15/03/2023 | 13/06/2023 | THREE MAA ENTERPRISE | 68.82 | 0 | 0 | 100
6 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | DHARALA PIPED WATER SUPPLY SCHEME | SM/14056 | New | DHARALA [RAGHUNATHPUR VILLAGE] Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000075/2023-2024 | 2054/BWD | 04/05/2023 | 02/08/2023 | BIPLAB GUHA | 65.39 | 0 | 0 | 100
7 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | DHARALA PIPED WATER SUPPLY SCHEME | SM/14056 | New | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 1724/F/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 5.24 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | DHARALA PIPED WATER SUPPLY SCHEME | SM/14056 | New | New service connection charges for Dharala PWSS TW-2 |  |  | BILL/01778/2023-2024 | BP-2023-24-286 | 26/12/2023 | 26/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.29 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | DHARALA PIPED WATER SUPPLY SCHEME | SM/14056 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Dharala Water Supply Scheme [ Block- Ausgram-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | Driller In-Charge | JUNIOR ENGINEER | ORD/000204/2023-2024 | 3048/CMD | 20/07/2023 | 01/05/2025 | J.S. CONSTRUCTION. | 29.71 | 0 | 0 | 70
10 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | DHARALA PIPED WATER SUPPLY SCHEME | SM/14056 | New | Acceptance cum Formal Work Order for Balance works related ( LDS , FHTCs, Road Restoration of Dharala Piped Water Supply Scheme under Aushgram-II Block, of Durgapur Water supply Division, PHE Dte. | Assistangt Engineer,Assistant Engineer-II,Assistant Engineer-II (Newly Charge takenover) | Contractual Junior Engineer_2 | ORD/000189/2024-2025 | 1609/DWSD | 26/11/2024 | 25/05/2025 | SARKAR AGENCY | 51.36 | 0 | 0 | 70
11 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | DHARALA PIPED WATER SUPPLY SCHEME | SM/14056 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 80
Total | [13 empty] | 347.6 | 0 | 0