## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | PHANRIJANGALPIPED WATER SUPPLY SCHEME | SM/14060 | New | Material Requisition To Resource Division |  |  | RTOR000369/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 13.24 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | PHANRIJANGALPIPED WATER SUPPLY SCHEME | SM/14060 | New | Material Requisition To Resource Division |  |  | RTOR000634/2023-2024 | 5090/BWD | 23/11/2023 | 23/11/2023 | Resource Division | 21.84 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | PHANRIJANGALPIPED WATER SUPPLY SCHEME | SM/14060 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 32.65 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | PHANRIJANGALPIPED WATER SUPPLY SCHEME | SM/14060 | New | New service connection charges for Phanrijangal PWSS TW 1 |  |  | BILL/01484/2023-2024 | BP-2023-24-184 | 04/10/2023 | 04/10/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.21 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | PHANRIJANGALPIPED WATER SUPPLY SCHEME | SM/14060 | New | New service connection charges for Phanrijangal PWSS TW-2 |  |  | BILL/01544/2023-2024 | BP-2023-24-213 | 03/11/2023 | 03/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.42 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | PHANRIJANGALPIPED WATER SUPPLY SCHEME | SM/14060 | New | PHANRIJANGAL Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000173/2023-2024 | 3030/BWD | 14/07/2023 | 10/01/2024 | SUPRIYA RAY | 271.24 | 228.47 | 84.23 | 35
7 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | PHANRIJANGALPIPED WATER SUPPLY SCHEME | SM/14060 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 80
8 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | PHANRIJANGALPIPED WATER SUPPLY SCHEME | SM/14060 | New | FORMAL WORK ORDER FOR Balance work for PHANRIJANGAL PWSS with sining of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block under DURGAPUR W/S DIVISION, PHE DTE. | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000267/2024-2025 | 281/DWSD | 17/02/2025 | 17/06/2025 | SUJAY KUMAR RAY | 101.85 | 0 | 0 | 0
Total | [13 empty] | 544.72 | 228.47 | 41.94