## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME | SM/14071 | New | Material Requisition To Resource Division |  |  | RTOR000206/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 11.86 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME | SM/14071 | New | Material Requisition To Resource Division |  |  | RTOR000450/2023-2024 | 3974/BWD | 08/09/2023 | 08/09/2023 | Resource Division | 1.93 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME | SM/14071 | New | Material Requisition To Resource Division |  |  | RTOR000598/2023-2024 | 4904/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 33.07 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME | SM/14071 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways for NRISINHAPUR Piped Water Supply Scheme under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000353/2023-2024 | 3066/BWD | 17/07/2023 | 01/04/2025 | M/S H.R. CONSTRUCTION | 401.37 | 0 | 0 | 50
5 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | NRISINHAPUR PIPED WATER SUPPLY SCHEME | SM/14071 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at NRISINHAPUR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000820/2023-2024 | 4097/CMD | 29/08/2023 | 28/09/2023 | P.K. ENGINEERING | 28.96 | 0 | 0 | 48
6 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME | SM/14071 | New | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 1724/D/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 2 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | NRISINHAPUR PIPED WATER SUPPLY SCHEME | SM/14071 | New | New service connection charges for Nrisinhapur PWSS TW-2 |  |  | BILL/00823/2024-2025 | BP-2024-25-318 | 30/09/2024 | 30/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.63 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | NRISINHAPUR PIPED WATER SUPPLY SCHEME | SM/14071 | New | New service connection charges for Nrisinhapur PWSS TW-1 |  |  | BILL/01826/2023-2024 | BP-2023-24-328 | 03/01/2024 | 03/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.56 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | NRISINHAPUR PIPED WATER SUPPLY SCHEME | SM/14071 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 80
10 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME | SM/14071 | New | Acceptance cum Formal Work Order for Balance work for NIRSINHAPUR Piped Water Supply Scheme i.e , Construction work LDS, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway etc. at 3rd Pump house site under AUSGRAM-II Block, District:- Purba-Bardhaman, under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000184/2024-2025 | 1594/DWSD | 25/11/2024 | 27/11/2025 | KIRON ENTERPRISE | 59.79 | 0 | 0 | 65
Total | [13 empty] | 646.43 | 0 | 0