## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | Material Requisition To Resource Division |  |  | RTOR000388/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 17.75 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | Material Requisition To Resource Division |  |  | RTOR000737/2023-2024 | 5236/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 18.78 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | Material Requisition To Resource Division |  |  | RTOR000025/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 79.1 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method for Trial Bore at Uchchagram under Krishnarampur PWSS (JJM) District:- Purba-Bardhaman, Under Durgapur W/S Division , PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000153/2024-2025 | 1418/DWSD | 03/10/2024 | 23/10/2024 | D.M.ENTERPRISE | 6.61 | 6.61 | 100 | 80
6 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | Material Requisition To Resource Division |  |  | RTOR000791/2023-2024 | 317/BWD | 24/01/2024 | 24/01/2024 | Resource Division | 43.39 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 1724/Q/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 4 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | NEW SERVICE CONNECTION FOR KRISHNARAMPUR PWSS PH-1. |  |  | BILL/02868/2023-2024 | BP-2023-24-606 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.75 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | NEW SERVICE CONNECTION FOR KRISHNARAMPUR PWSS PH-2. |  |  | BILL/02869/2023-2024 | BP-2023-24-607 | 06/03/2024 | 06/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.94 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | KRISHNARAMPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000403/2023-2024 | 3234/BWD | 26/07/2023 | 24/09/2025 | DUTTA ENTERPRISE | 661.41 | 249.5 | 37.72 | 80
11 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KRISHNARAMPUR Water Supply Scheme [ Block- GALSI-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000797/2023-2024 | 4085/CMD | 29/08/2023 | 28/09/2023 | BENGAL CONSTRUCTION. | 40.47 | 0 | 0 | 96
12 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | Acceptance cum Formal Work Order for Balance work for KRISHNARAMPUR Piped Water Supply Scheme i.e , Contruction of boundary walls with gates and land development, drain and internal pathway etc. at 3rd Pump house site & FHTC work under GALSI-I Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000167/2024-2025 | 1549/DWSD | 14/11/2024 | 11/08/2025 | JOY GURU ENTERPRISE | 43.27 | 0 | 0 | 100
13 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME | SM/14072 | New | Acceptance cum Formal Work Order for Sinking of 300 x 200 mm dia tube well 150 mtr depth by DR Rig method for trial bore at Sirorai and Bikrampur under Krishnarampur PWSS (JJM), Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000186/2024-2025 | 1597/DWSD | 25/11/2024 | 15/12/2024 | MANASH GHOSH | 10.17 | 10.17 | 100 | 100
Total | [13 empty] | 1026.07 | 266.27 | 25.95