## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/14073 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 39.22 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/14073 | New | Material Requisition To Resource Division |  |  | RTOR000292/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 6.23 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/14073 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000101/2024-2025 | 2398/CMD | 02/08/2024 | 31/10/2024 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/14073 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 25/12/2024 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/14073 | New | Material Requisition To Resource Division |  |  | RTOR000776/2023-2024 | 200/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 7.26 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/14073 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | AE(HQs) | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000727/2023-2024 | 4581/BWD | 16/10/2023 | 07/06/2026 | SAFECO ENTERPRISES | 1551.98 | 150.45 | 9.69 | 60
7 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME | SM/14073 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JAYKRISHNAPUR Water Supply Scheme [ Block- AUSGRAM-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000810/2023-2024 | 4094/CMD | 29/08/2023 | 08/04/2025 | MS S G ENTERPRISE | 27.68 | 0 | 0 | 96
Total | [13 empty] | 1738.35 | 150.45 | 8.65