## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME | SM/14074 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 53 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME | SM/14074 | New | Material Requisition To Resource Division |  |  | RTOR000328/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 13.76 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME | SM/14074 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME | SM/14074 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SHYAMSUNDARPUR Water Supply Scheme [ Block- GALSI-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000838/2023-2024 | 4112/CMD | 29/08/2023 | 28/09/2023 | CHOUDHURY ENTERPRISE | 27.73 | 0 | 0 | 48
5 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME | SM/14074 | New | Quotation for new electric service connection at Shyamsundarpur PH NO.-1 |  |  | BILL/01743/2023-2024 | BP-2023-24-246 | 07/12/2023 | 07/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.34 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME | SM/14074 | New | New service connection for SHYAMSUNDARPUR PWSS TW 2. |  |  | BILL/02447/2023-2024 | BP-2023-24-522 | 09/02/2024 | 09/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME | SM/14074 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMSUNDARPUR & BELGRAM Piped Water Supply Scheme under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer ,JUNIOR ENGINEER DURGAPUR SUB-DIVISION PHE DTE | ORD/000086/2023-2024 | 2147/BWD | 10/05/2023 | 09/05/2025 | MAHMOOD ASSOCIATES PVT. LTD. | 1172.24 | 57.5 | 4.91 | 78
Total | [13 empty] | 1369.48 | 57.5 | 4.2