## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | AE(HQs) | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000727/2023-2024 | 4581/BWD | 16/10/2023 | 07/06/2026 | SAFECO ENTERPRISES | 1551.98 | 182.42 | 11.75 | 60
2 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Aligram Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000747/2023-2024 | 4057/CMD | 29/08/2023 | 01/06/2025 | EASTERN INDIA SALES & SERVICE | 27.78 | 10.73 | 38.62 | 48
3 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Material Requisition To Resource Division |  |  | RTOR000607/2023-2024 | 4912/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 32.92 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Material Requisition To Resource Division |  |  | RTOR000551/2023-2024 | 4314/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 1.38 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.02.2024 to 31.07.2024).(Sl-01) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000287/2023-2024 | 106/DWSD | 31/01/2024 | 31/07/2024 | SUJIT ROY | 0.82 | 2.4 | 290.96 | 25
6 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Luxury Diesel Ambassadar Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2024 to 31.08.2024 (6 Months).(Sl-01) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000294/2023-2024 | 267/DWSD | 29/02/2024 | 31/08/2024 | PRAMIT CHATTERJEE | 0.82 | 2.37 | 288.04 | 0
7 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex, Banskopa,DGP-12 (w.e.f 18.02.2024 to 29.02.2024). (SL-02) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000314/2023-2024 | 186/DWSD | 15/02/2024 | 27/02/2024 | PRAMIT CHATTERJEE | 0.05 | 0.16 | 303.77 | 100
8 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.09.2024 to 28.02.2025 (6 Months).(Sl-01) | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000138/2024-2025 | 1244/DWSD | 30/08/2024 | 28/02/2025 | PRAMIT CHATTERJEE | 0.82 | 2.39 | 290.19 | 0
9 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation Order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.08.2024 to 31.01.2025).(Sl-01) | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000127/2024-2025 | 1079/DWSD | 30/07/2024 | 30/01/2025 | SUJIT ROY | 0.82 | 2.39 | 290.79 | 0
10 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 25/12/2024 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Material Requisition To Resource Division |  |  | RTOR000777/2023-2024 | 193/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 6.7 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | New service connection at Aligram W/S PWSS PH-1 |  |  | BILL/02312/2023-2024 | BP-2023-24-431 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.53 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | QUOTATION FOR NEW SERVICE CONNECTION AT ALIGRAM PWSS TW 2 |  |  | BILL/00371/2024-2025 | BP-2024-25-193 | 08/07/2024 | 08/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.58 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation Order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.02.2025 to 31.07.2025). | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000268/2024-2025 | 163/DWSD | 27/01/2025 | 27/07/2025 | SUJIT ROY | 0.82 | 0.4 | 48.49 | 0
15 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2025 to 31.05.2025 (3 Months). | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000280/2024-2025 | 340/DWSD | 27/02/2025 | 27/05/2025 | PRAMIT CHATTERJEE | 0.41 | 0.79 | 192.94 | 0
16 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.06.2025 to 31.08.2025 (3 Months). | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000043/2025-2026 | 853/DWSD | 29/05/2025 | 27/08/2025 | PRAMIT CHATTERJEE | 0.41 | 0 | 0 | 0
17 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Name of Work:- Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 16.09.2025 to 31.10.2025 (46 days) (Sl-01) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000139/2025-2026 | 1532/DWSD | 16/09/2025 | 01/11/2025 | TKB ENTERPRISE | 0.22 | 0 | 0 | 0
18 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 01.09.2025 to 28.02.2026 (181 days) (Sl-04) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000128/2025-2026 | 1381/DWSD | 26/08/2025 | 23/02/2026 | PRAMIT CHATTERJEE | 0.86 | 0 | 0 | 0
19 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 2/B/DWSD | 02/01/2025 | 02/01/2025 | Resource Division | 19.6 | 0 | 0 | 0
20 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at BHEDIA PWSS under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-I | Junior Engineer_3 | ORD/000231/2026-2027 | 872/DWSD | 29/06/2026 | 29/06/2027 | SUPRIYA RAY | 5.1 | 0 | 0 | 0
21 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at MANKAR (Z-I) PWSS under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-I | Junior Engineer_3 | ORD/000239/2026-2027 | 831/DWSD | 24/06/2026 | 24/06/2027 | SHUBHRA KANTI GHOSH | 5.1 | 0 | 0 | 0
22 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Repairing of damaged Pipeline (50mm,63mm,75mm,90 mm & 110mm dia HDPE) and FHTC repairing ALIGRAM PWSS of AUSGRAM Block -I at Deyasa Mouza under DWSD,PHE Dte.(Part-A) | Assistant Engineer-I | Junior Engineer_3 | ORD/000187/2026-2027 | 724/DWSD | 03/06/2026 | 18/06/2026 | RAJAT BARAN CHAND | 0.98 | 0 | 0 | 0
23 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at ALIGRAM PWSS under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-I | Junior Engineer_3 | ORD/000255/2026-2027 | 838/DWSD | 24/06/2026 | 24/06/2027 | RAJAT BARAN CHAND | 5 | 0 | 0 | 0
24 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at KHANO (Z-I) PWSS under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-I | Junior Engineer_3 | ORD/000253/2026-2027 | 837/DWSD | 24/06/2026 | 24/06/2027 | GHOSH ENTERPRISE | 4.98 | 0 | 0 | 0
25 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Supplying, delivery and installation of intercom dialing system in office and communicate with officials under office of the Executive Engineer, DWSD, PHE Dte under Surface based PWSS for Panagarh Industrial Park. (Sl - 03) | Assistant Engineer-I | Junior Engineer_3 | ORD/000261/2026-2027 | 945/DWSD | 08/07/2026 | 18/07/2026 | JOY GURU ENTERPRISE | 0.89 | 0 | 0 | 0
26 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Supplying, delivery and installation of different types of stationeries and colour printing etc for the office of the EE/DWSD/PHE Dte under Panagarh Industrial Park,Panagarh.(Sl-04) | Assistant Engineer-I | Junior Engineer_3 | ORD/000262/2026-2027 | 946/DWSD | 08/07/2026 | 15/07/2026 | ISHAAN ENTERPRISE | 0.98 | 0 | 0 | 0
27 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Day to day Guarding arrangment including Round -O-Clock guarding at Water Treatment Plant Site under Surface based water supply scheme for Panagarh Industrial Park under Durgapur Water Supply Division , PHE Dte.(w.e.f 01.08.2026 to 31.07.2027) | Assistant Engineer-II | Junior Engineer_3 | ORD/000287/2026-2027 | 1088/DWSD | 31/07/2026 | 31/07/2027 | SK. ALIM | 19.34 | 0 | 0 | 0
28 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at KHANDARI PWSS under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000227/2026-2027 | 869/DWSD | 25/06/2026 | 25/06/2027 | M/S NATIONAL CONSTRUCTION | 5.1 | 0 | 0 | 0
29 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at Purangaon PWSS (Zone-III) under Durgapur W/S Division, PHE Dte (w.e.f. 01.08.2026 to 31.07.2027) | Assistant Engineer-I | Junior Engineer_3 | ORD/000273/2026-2027 | 1072_DWSD | 30/07/2026 | 30/07/2027 | MANASH GHOSH | 4.95 | 0 | 0 | 0
30 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at SAUTA PWSS under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-I | JUNIOR ENGINEER-1 | ORD/000237/2026-2027 | 830/DWSD | 24/06/2026 | 24/06/2027 | SAIKAT RAY | 7.71 | 0 | 0 | 0
31 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for the work of engagement of 3 Nos Gr-D staff contractual through agency for 12 months as per categories for the office of the EE/DWSD/PHE Dte (w.e.f. 01.07.2026 to 31.7.2026) | Assistant Engineer-I | Junior Engineer_3 | ORD/000258/2026-2027 | 902/DWSD | 30/06/2026 | 31/07/2026 | SAIKAT RAY | 0.45 | 0 | 0 | 0
32 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at Shilla PWSS (ZONE-II) under Durgapur W/S Division, PHE Dte (w.e.f. 01.08.2026 to 31.07.2027) | Assistant Engineer-I | JUNIOR ENGINEER-1 | ORD/000272/2026-2027 | 1073/DWSD | 30/07/2026 | 30/07/2027 | M/S S. CHOUDHURY | 8.59 | 0 | 0 | 0
33 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for the work of Day to day Guarding arrangement including Round -O-Clock guarding at Water Treatment Plant Site under Surface based water supply scheme for Panagarh Industrial Park under Durgapur Water Supply Division , PHE Dte. (w.e.f 01/07/2026 to 31/07/2026) | Assistant Engineer-I | JUNIOR ENGINEER-1 | ORD/000276/2026-2027 | 813/DWSD | 22/06/2026 | 23/07/2026 | SK. ALIM | 1.48 | 0 | 0 | 0
34 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Repairing of damaged Pipeline (50mm,63mm,75mm,90 mm & 110mm dia HDPE) and FHTC repairing ALIGRAM PWSS of AUSGRAM Block -I at Konarpara Road under DWSD,PHE Dte.(Part-B) | Assistant Engineer-I | Junior Engineer_3 | ORD/000181/2026-2027 | 715/DWSD | 03/06/2026 | 18/06/2026 | RAJAT BARAN CHAND | 0.97 | 0 | 0 | 0
35 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of operration & maintenance of surface based W/S Scheme"Panagarh Industrial Park" under office of the Executive Engineer, Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 01.07.2026 to 31.12.2026 (181 days) (Sl-01) | Assistant Engineer-I | Junior Engineer_3 | ORD/000190/2026-2027 | 799/DWSD | 19/06/2026 | 20/12/2026 | SK. ALIM | 0.86 | 0 | 0 | 0
36 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Annual Operation and maintenance of different dia MS/DI distribution system pipe line (Zone-I and II) Panagarh Industrial Park area under Surface based PWSS for Panagarh Industrial Park, of Durgapur W/s Division, PHE Dte (w.e.f 01.08.2026 to 31.07.2027) | Assistant Engineer-I | JUNIOR ENGINEER-1,Junior Engineer_3 | ORD/000284/2026-2027 | 1086/DWSD | 31/07/2026 | 31/07/2027 | SK. ABDUL HALIM | 25.27 | 0 | 0 | 0
37 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Sinking of 100 mm. dia. 80m. deep Tube wells using PVC pipes with installation of submersible pump (for 01 No. new) in Panagar Industrial park under Durgapur W/S Division, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer_3 | ORD/000189/2026-2027 | 729/DWSD | 03/06/2026 | 18/06/2026 | SIDDHARTH ENTERPRISE | 1 | 0 | 0 | 0
38 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Urgent basis repairing and restoration work of maintenance of damaged 150/200/250 mm dia DI and HDPE distribution pipeline at Pandudaha, Fatepur and Kosba under Krishnarampur PWSS, block-Galsi-I during road flank widening work including RCC bridge of WBSRDA under control of DWSD, PHE Dte. (Part-A) (Sl-11) | Assistant Engineer-I | JUNIOR ENGINEER-1 | ORD/000268/2026-2027 | 1095/DWSD | 31/07/2026 | 15/08/2026 | JOY GURU ENTERPRISE | 0.96 | 0 | 0 | 0
Total | [13 empty] | 1806.83 | 204.06 | 11.29