## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Material Requisition To Resource Division |  |  | RTOR000607/2023-2024 | 4912/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 32.92 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Material Requisition To Resource Division |  |  | RTOR000551/2023-2024 | 4314/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 1.38 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.02.2024 to 31.07.2024).(Sl-01) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000287/2023-2024 | 106/DWSD | 31/01/2024 | 31/07/2024 | SUJIT ROY | 0.82 | 2.4 | 290.96 | 25
4 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Luxury Diesel Ambassadar Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2024 to 31.08.2024 (6 Months).(Sl-01) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000294/2023-2024 | 267/DWSD | 29/02/2024 | 31/08/2024 | PRAMIT CHATTERJEE | 0.82 | 2.37 | 288.04 | 0
5 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex, Banskopa,DGP-12 (w.e.f 18.02.2024 to 29.02.2024). (SL-02) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000314/2023-2024 | 186/DWSD | 15/02/2024 | 27/02/2024 | PRAMIT CHATTERJEE | 0.05 | 0.16 | 303.77 | 100
6 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | Driller In-Charge | JUNIOR ENGINEER | ORD/000398/2024-2025 | 2764/CMD | 26/09/2024 | 25/12/2024 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Material Requisition To Resource Division |  |  | RTOR000777/2023-2024 | 193/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 6.7 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | QUOTATION FOR NEW SERVICE CONNECTION AT ALIGRAM PWSS TW 2 |  |  | BILL/00371/2024-2025 | BP-2024-25-193 | 08/07/2024 | 08/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.58 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | New service connection at Aligram W/S PWSS PH-1 |  |  | BILL/02312/2023-2024 | BP-2023-24-431 | 29/01/2024 | 29/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.53 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ausgram-I | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Aligram Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000747/2023-2024 | 4057/CMD | 29/08/2023 | 01/06/2025 | EASTERN INDIA SALES & SERVICE | 27.78 | 10.73 | 38.62 | 48
11 | PURBA BARDHAMAN | Ausgram-I | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | AE(HQs) | JUNIOR ENGINEER R.W.S. BURDWAN SUB-DIVISION PHE DTE | ORD/000727/2023-2024 | 4581/BWD | 16/10/2023 | 07/06/2026 | SAFECO ENTERPRISES | 1551.98 | 182.42 | 11.75 | 60
12 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.09.2024 to 28.02.2025 (6 Months).(Sl-01) | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000138/2024-2025 | 1244/DWSD | 30/08/2024 | 28/02/2025 | PRAMIT CHATTERJEE | 0.82 | 2.39 | 290.19 | 0
13 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation Order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.08.2024 to 31.01.2025).(Sl-01) | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000127/2024-2025 | 1079/DWSD | 30/07/2024 | 30/01/2025 | SUJIT ROY | 0.82 | 2.39 | 290.79 | 0
14 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation Order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.02.2025 to 31.07.2025). | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000268/2024-2025 | 163/DWSD | 27/01/2025 | 27/07/2025 | SUJIT ROY | 0.82 | 0.4 | 48.49 | 0
15 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2025 to 31.05.2025 (3 Months). | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000280/2024-2025 | 340/DWSD | 27/02/2025 | 27/05/2025 | PRAMIT CHATTERJEE | 0.41 | 0.79 | 192.94 | 0
16 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.06.2025 to 31.08.2025 (3 Months). | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000043/2025-2026 | 853/DWSD | 29/05/2025 | 27/08/2025 | PRAMIT CHATTERJEE | 0.41 | 0 | 0 | 0
17 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Name of Work:- Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 16.09.2025 to 31.10.2025 (46 days) (Sl-01) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000139/2025-2026 | 1532/DWSD | 16/09/2025 | 01/11/2025 | TKB ENTERPRISE | 0.22 | 0 | 0 | 0
18 | PURBA BARDHAMAN | Ausgram-I | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME | SM/14927 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 01.09.2025 to 28.02.2026 (181 days) (Sl-04) | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000128/2025-2026 | 1381/DWSD | 26/08/2025 | 23/02/2026 | PRAMIT CHATTERJEE | 0.86 | 0 | 0 | 0
Total | [13 empty] | 1687.5 | 204.06 | 12.09