## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 11.55 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Material Requisition To Resource Division |  |  | RTOR000294/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 12.41 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Material Requisition To Resource Division |  |  | RTOR000758/2023-2024 | 5241/BWD | 30/11/2023 | 30/11/2023 | Resource Division | 18.5 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | New service connection charges for Sar PWSS TW-2 |  |  | BILL/01463/2023-2024 | BP-2023-24-162 | 18/09/2023 | 18/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.45 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | New service connection charges for Sar PWSS TW-1 |  |  | BILL/01464/2023-2024 | BP-2023-24-163 | 18/09/2023 | 18/09/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.8 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Acceptance cum Formal Work Order for Road Restoration ,Land development with access road & allied works for Augmentation of SAR PWSS , Ausgram-II Block under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_4,Contractual Junior Engineer_5 | ORD/000175/2024-2025 | 1616/DWSD | 26/11/2024 | 24/02/2025 | SAIKAT RAY | 10.77 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | SAR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000094/2023-2024 | 2231/BWD | 16/05/2023 | 15/05/2024 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 193.73 | 0 | 0 | 100
8 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Material Requisition To Resource Division |  |  | RTOR000015/2024-2025 | 1724/K/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 0.55 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 80
10 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Acceptance cum Formal Work Order for SATINANDI Piped Water Supply Scheme with INSTALLATION OF BARBED WIRE, FHTC ,Road restoration ,DEMOLITION WORK & land development with road at TW site under Galsi-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_4,Junior Engineer_3 | ORD/000183/2024-2025 | 1620/DWSD | 26/11/2024 | 18/10/2025 | A K SIKDAR | 79.05 | 0 | 0 | 70
11 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SAR PIPED WATER SUPPLY SCHEME | SM/14929 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sar Water Supply Scheme [ Block-Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000588/2023-2024 | 3924/CMD | 22/08/2023 | 21/09/2023 | D.K. ELECTRIC | 27.75 | 0 | 0 | 98
Total | [13 empty] | 459.83 | 0 | 0