## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 73.04 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Material Requisition To Resource Division |  |  | RTOR000289/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 16.34 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Material Requisition To Resource Division |  |  | RTOR000615/2023-2024 | 4878/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 30.36 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | New service connection charges for Jalkandar PWSS TW-1 |  |  | BILL/01781/2023-2024 | BP-2023-24-290 | 26/12/2023 | 26/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.59 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & Installation of Submersible Pumping Machinery, and piping works for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | Driller In-Charge |  | ORD/001628/2023-2024 | 40/DIC/BMSD(D) | 15/01/2024 | 30/01/2024 | H.K. DAS & CO. | 0.38 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & Delivery of actuator valve for Tube Well No: 02 at JALKHANDAR Water Supply Scheme [Block- AUSGRAM -2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/001634/2023-2024 | 100/DIC/BMSD(D) | 12/02/2024 | 19/02/2024 | H.K. DAS & CO. | 0.97 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & delivery of the following Electrical & Mechanical accessories for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2) under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/001625/2023-2024 | 23/DIC/BMSD(D) | 05/01/2024 | 12/01/2024 | H.K. DAS & CO. | 0.93 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & Delivery of Submersible Pumping Machinery for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [Block- AUSGRAM -2] under CMD, PHE Dte.,Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/001623/2023-2024 | 349/DIC/BMSD(D) | 22/12/2023 | 29/12/2023 | H.K. DAS & CO. | 0.8 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & delivery of Electrical & Mechanical accessories for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.· Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/001631/2023-2024 | 45/DIC/BMSD(D) | 19/01/2024 | 26/01/2024 | H.K. DAS & CO. | 0.63 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Quotation for new service connection at Jalikandar W/S Scheme for PH No-2 |  |  | BILL/01824/2023-2024 | BP-2023-24-330 | 03/01/2024 | 03/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.52 | 0 | 0 | 0
11 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Contractual Junior Engineer_1,Contractual Junior Engineer_2,Contractual Junior Engineer_3,Contractual Junior Engineer_4,Contractual Junior Engineer_5,JUNIOR ENGINEER-1,JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000286/2024-2025 | 493/DWSD | 19/03/2025 | 20/09/2025 | MANASH GHOSH | 745.87 | 0 | 0 | 1
12 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME | SM/14953 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JALKANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000916/2023-2024 | 4180/CMD | 29/08/2023 | 28/09/2023 | SOUNAK ENTERPRISE | 28.48 | 0 | 0 | 96
Total | [13 empty] | 907.92 | 0 | 0