## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | KALAIJHUTI PIPED WATER SUPPLY SCHEME | SM/14954 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KALAIJHUTI Water Supply Scheme [ Block- AUSGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000046/2023-2024 | 2509/CMD | 02/06/2023 | 02/07/2023 | SOUNAK ENTERPRISE | 27.79 | 0 | 0 | 30
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | KALAIJHUTI PIPED WATER SUPPLY SCHEME | SM/14954 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 1.78 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | KALAIJHUTI PIPED WATER SUPPLY SCHEME | SM/14954 | New | Material Requisition To Resource Division |  |  | RTOR000174/2023-2024 | 2155/BWD | 10/05/2023 | 10/05/2023 | Resource Division | 16.15 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | KALAIJHUTI PIPED WATER SUPPLY SCHEME | SM/14954 | New | Material Requisition To Resource Division |  |  | RTOR000616/2023-2024 | 4876/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 30.36 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | KALAIJHUTI PIPED WATER SUPPLY SCHEME | SM/14954 | New | New service connection charges for Kalaijhuti PWSS TW-1 |  |  | BILL/00760/2023-2024 | BP-2023-24-60 | 17/07/2023 | 17/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.51 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | KALAIJHUTI PIPED WATER SUPPLY SCHEME | SM/14954 | New | KALAIJHUTI [Kalaijhuti Village (Node Point 1 to 84)] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000804/2022-2023 | 1565/BWD | 30/03/2023 | 28/06/2023 | PABITRA KUMAR SAMANTA | 93 | 0 | 0 | 100
7 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | KALAIJHUTI PIPED WATER SUPPLY SCHEME | SM/14954 | New | Acceptance cum Formal Work Order for Additional work for laying of Extension or Laying of parallel pipeline,providing FHTC,Road Restoration work, Land development under Kalaijhuti PWSS in Ausgram -II Block under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | Contractual Junior Engineer_5 | ORD/000176/2024-2025 | 1622/DWSD | 26/11/2024 | 01/03/2025 | ROY CONSTRUCTION | 27.08 | 0 | 0 | 40
Total | [13 empty] | 198.68 | 0 | 0