## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 46.65 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | Material Requisition To Resource Division |  |  | RTOR000326/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 13.13 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | Material Requisition To Resource Division |  |  | RTOR000620/2023-2024 | 4887/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 30.36 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | New service connection charges for Suata PWSS TW-2 |  |  | BILL/01701/2023-2024 | BP-2023-24-233 | 20/11/2023 | 20/11/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.29 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | Acceptance cum Formal Work Order for Balance works of 160 mm dia HDPE rising main at JOYRAMPUR area and etc. allied works at SUATA of Ausgram -II Block of SUATA W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000099/2024-2025 | 1012/DWSD | 16/07/2024 | 14/10/2024 | SAIKAT RAY | 67.88 | 0 | 0 | 100
6 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | Acceptance cum Formal Work Order for the work of " Balance work for sinking of 250 x 150mm dia T/W, P/H, Boundary wall, DI RM and LLDS for proposed 3rd T/W and other allied works under Sauta PWSS, Block- Aushgram-II, Dist-Purba Bardhaman under Durgapur W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000001/2024-2025 | 768/DWSD | 06/06/2024 | 21/07/2024 | SAIKAT RAY | 94.93 | 0 | 0 | 70
7 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 1724/I/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 2.16 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | QUOTATION FOR NEW SERVICE CONNECTION FOR SUATA (ADDL TW)PWSS, TW 2 |  |  | BILL/00328/2024-2025 | BP-2024-25-162 | 01/07/2024 | 01/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.68 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | Quotation for new service connection at Suata W/S Scheme for PH No-1. |  |  | BILL/01821/2023-2024 | BP-2023-24-331 | 03/01/2024 | 03/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Chora, Kalaijhuti & others water supply scheme under Ausgram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000143/2024-2025 | 2405/CMD | 02/08/2024 | 31/10/2024 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 95.26 | 0 | 0 | 80
11 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | SUATA Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000494/2023-2024 | 3524/BWD | 10/08/2023 | 30/04/2025 | SAIKAT RAY | 615.97 | 0 | 0 | 45
12 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | SUATA PIPED WATER SUPPLY SCHEME | SM/14974 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Suata Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000748/2023-2024 | 4058/CMD | 29/08/2023 | 28/09/2023 | DEY ENTERPRISE | 27.79 | 0 | 0 | 96
Total | [13 empty] | 1010.52 | 0 | 0