## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | SM/15176 | Augmentation | Quotation for new service connection at Amragarah PWSS TW-2 (Aug). |  |  | BILL/00899/2024-2025 | BP-2024-25-338 | 04/10/2024 | 04/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.59 | 0 | 0 | 0
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | SM/15176 | Augmentation | Quotation for new service connection at Amragarh PWSS TW-3 |  |  | BILL/01091/2024-2025 | BP-2024-25-401 | 22/11/2024 | 22/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.49 | 0 | 0 | 0
3 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | SM/15176 | Augmentation | Making illumination arrangement and mise works at AMRARGARH and adjacent water supply scheme ausgram-II BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000477/2024-2025 | 2955/CMD | 20/11/2024 | 19/01/2025 | A.S. ENTERPRISE | 22.81 | 0 | 0 | 50
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | SM/15176 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of AMRARGARH[AUSGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001086/2023-2024 | 4509/CMD | 06/10/2023 | 02/06/2025 | S.K. ENTERPRISE | 24.39 | 0 | 0 | 80
Total | [13 empty] | 60.29 | 0 | 0