## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | SM/15176 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of AMRARGARH[AUSGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/001086/2023-2024 | 4509/CMD | 06/10/2023 | 02/06/2025 | S.K. ENTERPRISE | 24.39 | 6.11 | 25.05 | 80
2 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | SM/15176 | Augmentation | Making illumination arrangement and mise works at AMRARGARH and adjacent water supply scheme ausgram-II BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | Driller In-Charge | Junior Engineer | ORD/000477/2024-2025 | 2955/CMD | 20/11/2024 | 19/01/2025 | A.S. ENTERPRISE | 22.81 | 0 | 0 | 50
3 | PURBA BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | SM/15176 | Augmentation | Formal Work Order for Source Augmentation of Amarargarh Piped Water Supply Scheme [Tube Well, Pump House, Bounday Wall, Rising Main, FHTC etc], Block- Ausgram-II, Dist- purba Bardhaman under Durgapur W/S Division, PHE Dte | Assistant Engineer-II | Contractual Junior Engineer_2 | ORD/000104/2024-2025 | 1014/DWSD | 16/07/2024 | 03/10/2025 | BIPLAB GUHA | 109.16 | 34.32 | 31.44 | 100
4 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | SM/15176 | Augmentation | Quotation for new service connection at Amragarh PWSS TW-3 |  |  | BILL/01091/2024-2025 | BP-2024-25-401 | 22/11/2024 | 22/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.49 | 0 | 0 | 0
5 | PURBA BARDHAMAN |  | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | SM/15176 | Augmentation | Quotation for new service connection at Amragarah PWSS TW-2 (Aug). |  |  | BILL/00899/2024-2025 | BP-2024-25-338 | 04/10/2024 | 04/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.59 | 0 | 0 | 0
6 | PURBA BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | SM/15176 | Augmentation | Repairing of damaged Pipeline (50mm,63mm,75mm,90 mm,110mm & 140mm dia HDPE) Amrarghar PWSS of Aushgram -II Block under DWSD,phe,Dte. (Sl-09) | Assistant Engineer-I | JUNIOR ENGINEER-4 | ORD/000283/2026-2027 | 1081/DWSD | 30/07/2026 | 14/08/2026 | ISHAAN ENTERPRISE | 1 | 0 | 0 | 0
7 | PURBA BARDHAMAN |  | Durgapur W/S Division | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME | SM/15176 | Augmentation | Annual O and Mtc of distribution system, rising main, sluice valves including operation of sluice valves at TAHERPUR PWSS (ZONE-III) under Durgapur W/S Division, PHE Dte (w.e.f. 01.07.2026 to 30.06.2027) | Assistant Engineer-II | Junior Engineer_3 | ORD/000256/2026-2027 | 832/DWSD | 24/06/2026 | 24/06/2027 | GHOSH & ROY ENTERPRISE | 5 | 0 | 0 | 0
Total | [13 empty] | 175.44 | 40.43 | 23.04