## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | MARO PIPED WATER SUPPLY SCHEME | SM/15579 | New | MARO Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000175/2023-2024 | 2569/BWD | 01/06/2023 | 29/09/2023 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 113.32 | 90.81 | 80.14 | 90
2 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | MARO PIPED WATER SUPPLY SCHEME | SM/15579 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MARO Water Supply Scheme [ Block- GALSI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000903/2023-2024 | 4167/CMD | 29/08/2023 | 28/09/2023 | CHOUDHURY ENTERPRISE | 28.54 | 11.6 | 40.66 | 48
3 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | MARO PIPED WATER SUPPLY SCHEME | SM/15579 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1962/BWD | 25/04/2023 | 25/04/2023 | Resource Division | 3.65 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | MARO PIPED WATER SUPPLY SCHEME | SM/15579 | New | Material Requisition To Resource Division |  |  | RTOR000340/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 7 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | MARO PIPED WATER SUPPLY SCHEME | SM/15579 | New | Material Requisition To Resource Division |  |  | RTOR000605/2023-2024 | 4910/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 12.78 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | MARO PIPED WATER SUPPLY SCHEME | SM/15579 | New | Different works related (sinking of Tube-wells at Maro Dakshin Para, LDSs, Interconnections, FHTCs, Construction of MARO Piped Water Supply Scheme for obstruction of Railway under Galsi-I Block, of Durgapur Sub Division, under Burdwan Division, PHE. Dte. | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000334/2024-2025 | 2895/BWD | 23/07/2024 | 29/07/2025 | PREMANANDA ROY BISWAS | 42.93 | 0 | 0 | 90
7 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | MARO PIPED WATER SUPPLY SCHEME | SM/15579 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | MARO PIPED WATER SUPPLY SCHEME | SM/15579 | New | New service connection for MARO PWSS, PG-1. |  |  | BILL/02485/2023-2024 | BP-2023-24-537 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.06 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | MARO PIPED WATER SUPPLY SCHEME | SM/15579 | New | QUOTATION FOR NEW SERVICE CONNECTION AT MARO PWSS P.H-2 UNDER CMD, PHE, Dte. |  |  | BILL/00261/2025-2026 | 73 | 04/08/2025 | 04/08/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.99 | 0 | 0 | 0
10 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | MARO PIPED WATER SUPPLY SCHEME | SM/15579 | New | Digital structurization of pipeline alignment through survey and preparation of maps for 3 (Three) Nos. Piped Water Supply Schemes of Ausgram-I & Galsi-I Blocks for execution of the Sujalam Bharat Mobile application in Purba Bardhaman District under the jurisdiction of Durgapur Water Supply Division, PHE Directorate.(Sibada, Bhota, Maro) (Sl-04) | Assistant Engineer-I | JUNIOR ENGINEER-4 | ORD/000289/2026-2027 | 1098/DWSD | 31/07/2026 | 15/08/2026 | HORIZEN | 0.95 | 0 | 0 | 0
Total | [13 empty] | 305.63 | 102.42 | 33.51