## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BARADOBA PIPED WATER SUPPLY SCHEME | SM/18230 | New | Material Requisition To Resource Division |  |  | RTOR000233/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 11.17 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BARADOBA PIPED WATER SUPPLY SCHEME | SM/18230 | New | Material Requisition To Resource Division |  |  | RTOR000438/2023-2024 | 3849/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 1.22 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BARADOBA PIPED WATER SUPPLY SCHEME | SM/18230 | New | Material Requisition To Resource Division |  |  | RTOR000612/2023-2024 | 4933/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 16.68 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | BARADOBA PIPED WATER SUPPLY SCHEME | SM/18230 | New | New service connection charges for Baradoba PWSS TW-1 |  |  | BILL/01349/2023-2024 | BP-2023-24-129 | 21/08/2023 | 21/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.34 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | BARADOBA PIPED WATER SUPPLY SCHEME | SM/18230 | New | Acceptance cum Formal Work Order for BARADOBA Piped Water Supply Scheme with FHTC ,Road restoration under AUSGRAM-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte | Assistant Engineer-I | Contractual Junior Engineer_4 | ORD/000173/2024-2025 | 1619/DWSD | 26/11/2024 | 25/01/2025 | SAIKAT RAY | 15.24 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Ausgram-II | Durgapur W/S Division | BARADOBA PIPED WATER SUPPLY SCHEME | SM/18230 | New | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 1724/R/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 0.77 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | BARADOBA PIPED WATER SUPPLY SCHEME | SM/18230 | New | New service connection charges for Baradoba PWSS TW-2 |  |  | BILL/01825/2023-2024 | BP-2023-24-334 | 03/01/2024 | 03/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.77 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Ausgram-II | Central Mechanical | BARADOBA PIPED WATER SUPPLY SCHEME | SM/18230 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at BARADOBA Water Supply Scheme [Block - AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000449/2023-2024 | 3699/CMD | 07/08/2023 | 02/05/2026 | M/S, S.DAS AND ENTERPRISE. | 21.33 | 0 | 0 | 90
9 | PURBA BARDHAMAN | Ausgram-II | Burdwan Division | BARADOBA PIPED WATER SUPPLY SCHEME | SM/18230 | New | BARADOBA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSHGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer | ORD/000188/2023-2024 | 2677/BWD | 08/06/2023 | 27/08/2024 | THREE MAA ENTERPRISE | 109.1 | 0 | 0 | 100
Total | [13 empty] | 185.62 | 0 | 0