## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | Material Requisition To Resource Division |  |  | RTOR000343/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 2.41 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | Material Requisition To Resource Division |  |  | RTOR000563/2023-2024 | 4937/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 54.72 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | Material Requisition To Resource Division |  |  | RTOR000446/2023-2024 | 3844/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 251.04 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | Shifting of 11KV Line of Mohanpur PWSS under Burdwan Division, PHE Dte. |  |  | BILL/01080/2023-2024 | 1055/JJM | 13/12/2023 | 13/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.33 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 1724/N/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 11.33 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | New service connection for Mohanpur PWSS . |  |  | BILL/02410/2023-2024 | BP-2023-24-507 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.83 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | New service connection for Mohanpur PWSS . |  |  | BILL/02408/2023-2024 | BP-2023-24-506 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.86 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | MOHANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer2, Durgapur Sub-Division, PHE Dte. | ORD/000386/2023-2024 | 3149/BWD | 20/07/2023 | 01/09/2025 | MD HASIN | 963.53 | 0 | 0 | 80
10 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | FORMAL WORK ORDER FOR MOHANPUR Piped Water Supply Scheme with Inter-connection, LDS, FHTC ,Road restoration & construction of switch rooms & boundary walls with gates, land development with road at TW site under Galsi-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte | Assistant Engineer-II | Contractual Junior Engineer_4 | ORD/000220/2024-2025 | 41/DWSD | 08/01/2025 | 08/12/2025 | MD.HASIN | 148.94 | 0 | 0 | 70
11 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | MOHANPUR PIPED WATER SUPPLY SCHEME | SM/18242 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-4 at MOHANPUR Water Supply Scheme [ BLOCK- GALSI-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/001388/2024-2025 | 881/CMD | 26/03/2025 | 25/05/2025 | CHOUDHURY ENTERPRISE | 12.88 | 0 | 0 | 0
Total | [13 empty] | 1543.29 | 0 | 0