## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Material Requisition To Resource Division |  |  | RTOR000380/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 8.77 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Material Requisition To Resource Division |  |  | RTOR000537/2023-2024 | 4297/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 1.83 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Material Requisition To Resource Division |  |  | RTOR000553/2023-2024 | 4445/BWD | 09/10/2023 | 09/10/2023 | Resource Division | 14.51 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 30/03/2024 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 0 | 0 | 100
5 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Material Requisition To Resource Division |  |  | RTOR000765/2023-2024 | 198/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 16.34 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | New service connection charges for Khano PWSS Z-I TW-2 |  |  | BILL/00821/2024-2025 | BP-2024-25-323 | 03/10/2024 | 03/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.9 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Quotation for new service connection for Khano PWSS PH 3. |  |  | BILL/00220/2024-2025 | BP-2024-25-110 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.74 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe Carring Bridge with Pipe supporting structure under TAHERPUR and KHANO Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2,Junior Engineer_3 | ORD/000158/2024-2025 | 1506/DWSD | 05/11/2024 | 29/06/2025 | MANASH GHOSH | 1114.23 | 0 | 0 | 60
9 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone-1 & 2, T.W. No.- 1 & 2 at KHANO Water Supply Scheme [ BLOCK- Galsi-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000559/2024-2025 | 3089/CMD | 10/12/2024 | 03/08/2025 | M.S. ENTERPRISE | 50.29 | 0 | 0 | 24
10 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Execution and payment of wayleave permission with railway services for crossing of portable water supply PWSSat Khano under Khano PWSS under DWSD,PHE Dte | Assistant Engineer-I | JUNIOR ENGINEER-2 | ORD/000011/2025-2026 | 657/DWSD | 21/04/2025 | 02/11/2025 | MANASH GHOSH | 7.09 | 0 | 0 | 71
11 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Taherpur-khano sub surface water supply scheme under Central Mechanical Division PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000784/2024-2025 | 480/CMD | 06/02/2025 | 22/04/2025 | GLACIER ENGINEERING CO | 105.71 | 0 | 0 | 0
12 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Acceptance cum Formal Work Order for Design Engineering Services of Survey, General arrangement drawing, Pile foundation design and drawings, Pipe Pedestal and BOM, Structural design design and drawing, Fabrication drawings for 26 Numbers different dia meter pipe crossing Pipe Bridge at "PURANGAN (Zone-I, II, III), 11 Nos. Mouzas under PURSHA and UCHCHGRAM, SHILLA (Zone-I, II, III, IV), TAHER PUR (Zone-I, II, III) and KHANO (Zone-I and II) sites under Durgapur W/S Division,PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000105/2024-2025 | 1058/DWSD | 25/07/2024 | 21/04/2025 | ASTER CONSULTANCY | 47.43 | 0 | 0 | 70
Total | [13 empty] | 1497.18 | 0 | 0