## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Material Requisition To Resource Division |  |  | RTOR000380/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 8.77 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Material Requisition To Resource Division |  |  | RTOR000537/2023-2024 | 4297/BWD | 29/09/2023 | 29/09/2023 | Resource Division | 1.83 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Material Requisition To Resource Division |  |  | RTOR000553/2023-2024 | 4445/BWD | 09/10/2023 | 09/10/2023 | Resource Division | 14.51 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 30/03/2024 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 21.53 | 19 | 100
5 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Material Requisition To Resource Division |  |  | RTOR000765/2023-2024 | 198/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 16.34 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | New service connection charges for Khano PWSS Z-I TW-2 |  |  | BILL/00821/2024-2025 | BP-2024-25-323 | 03/10/2024 | 03/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.9 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Quotation for new service connection for Khano PWSS PH 3. |  |  | BILL/00220/2024-2025 | BP-2024-25-110 | 28/05/2024 | 28/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.74 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Sub Surface Based Piped Water Supply Scheme with LDS, FHTC, Construction of different capacity RCC OHRs with 20.0 mtr. with Staging height including soil investigation, Construction of CWR, Chlorine Room, Guard Room, Sub Station Building, High Lift Pump House Boundary walls with gates, land development, drain and internal pathway of KHANO Piped Water Supply Scheme under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL |  |  | ORD/000496/2023-2024 | 3526/BWD | 10/08/2023 | 07/11/2025 | MEGHDOOT GHOSH | 1088.86 | 305.99 | 28.1 | 55
9 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Acceptance cum Formal Work Order work oof Sinking of 3 Nos 300 x 200 mm dia T/W 150mtr and Construction of P/H cum switch room chlorine room (4 nos) under KHANO PWSS (JJM), Block- Galsi-II, Dist:- Purba Bardhaman. | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000308/2023-2024 | 371/DWSD | 15/03/2024 | 13/06/2025 | MEGHDOOT GHOSH | 80.19 | 30.2 | 37.66 | 40
10 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe Carring Bridge with Pipe supporting structure under TAHERPUR and KHANO Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000158/2024-2025 | 1506/DWSD | 05/11/2024 | 29/06/2025 | MANASH GHOSH | 1114.23 | 342.4 | 30.73 | 60
11 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Formal Work Order for Additional Work of Soil investigation and construction of CWR cum Pump House with M.S structural work, Substation, Chlorine Room etc. Land Development of H/W site, drain and internal path way, concrete road and Bituminous Road Restoration, laying of M.S pipe, FHTC with platfrom and necessary allied works of Sub Surface based Taherpur and Khano PWSS (JJM) under Galsi-II Block, Dist- Purba Bardhaman, under Durgapur W/S Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000161/2024-2025 | 1507/DWSD | 05/11/2024 | 31/10/2025 | S & P ENTERPRISE | 811.59 | 0 | 0 | 35
12 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone-1 & 2, T.W. No.- 1 & 2 at KHANO Water Supply Scheme [ BLOCK- Galsi-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000559/2024-2025 | 3089/CMD | 10/12/2024 | 03/08/2025 | M.S. ENTERPRISE | 50.29 | 0 | 0 | 24
13 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries including intake (Low lift) pumping machineries, High Lift pumping machineries, 0-1 kg/hour gaseous chlorination system and illumination arrangement of Taherpur & Khano Sub-Surface Based Piped Water Supply Scheme under Purba Bardhaman District PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000002/2025-2026 | 904/CMD | 04/04/2025 | 18/06/2025 | SINHA ELECTRICALS | 329.09 | 0 | 0 | 0
14 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Execution and payment of wayleave permission with railway services for crossing of portable water supply PWSSat Khano under Khano PWSS under DWSD,PHE Dte | Assistant Engineer-I | JUNIOR ENGINEER-2 | ORD/000011/2025-2026 | 657/DWSD | 21/04/2025 | 02/11/2025 | MANASH GHOSH | 7.09 | 5.26 | 74.21 | 71
15 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME | SM/18313 | New | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Taherpur-khano sub surface water supply scheme under Central Mechanical Division PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000784/2024-2025 | 480/CMD | 06/02/2025 | 22/04/2025 | GLACIER ENGINEERING CO | 105.71 | 0 | 0 | 0
Total | [13 empty] | 3759.48 | 705.39 | 18.76