## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | LOAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] | Assistant Engineer, Durgapur Sub Division, P.H.E. Dte | Junior Engineer1, Durgapur Sub-Division, PHE Dte. | ORD/000419/2023-2024 | 3290/BWD | 31/07/2023 | 30/07/2024 | M/S ASHA CONSTRUCTION | 824.72 | 255.05 | 30.93 | 15
2 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | Material Requisition To Resource Division |  |  | RTOR000395/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 3.72 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | Material Requisition To Resource Division |  |  | RTOR000444/2023-2024 | 3845/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 164.37 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | Material Requisition To Resource Division |  |  | RTOR000560/2023-2024 | 4918/BWD | 10/11/2023 | 10/11/2023 | Resource Division | 60.13 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | Acceptance cum Formal Work Order for Balance work of dismantling concrete road including mending work, construction of approach road by fill up stone dust , bolders etc. and allied works under LOAPUR Water Supply Scheme, Galsi-I Block, District:- Purba-Bardhaman. | Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000166/2024-2025 | 1595/DWSD | 25/11/2024 | 25/03/2025 | M/S ASHA CONSTRUCTION | 95.37 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 1724/S/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 17.89 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | NEW SERVICE CONNECTION FOR LOHAPUR PWSS PH-1. |  |  | BILL/03137/2023-2024 | BP-2023-24-651 | 20/03/2024 | 20/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.92 | 0 | 0 | 0
9 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | LOAPUR PIPED WATER SUPPLY SCHEME | SM/18323 | New | QUOTATION FOR NEW SERVICE CONNECTION AT LOAPUR PWSS P.H-2 |  |  | BILL/01293/2024-2025 | BP-2024-25-427 | 31/01/2025 | 31/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.7 | 0 | 0 | 0
Total | [13 empty] | 1270.25 | 255.05 | 20.08