## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Material Requisition To Resource Division |  |  | RTOR000309/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 11.39 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Material Requisition To Resource Division |  |  | RTOR000440/2023-2024 | 3847/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 460.56 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi-I | Central Drilling | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Construction of Tube Well (300 MM x 200 MM x Depth 500 Mtr) for Shilla W/S Scheme(T/W -I) Zone-IV, Block- Galsi-I, Purba Bardhaman District by Central Drilling Division, P.H. Engineering Dte. | Driller In Charge | Junior Engineer | ORD/000216/2023-2024 | 2236/CDD | 11/03/2024 | 10/05/2024 | SATYAJIT GHOSH | 39.72 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. |  |  | ORD/000872/2023-2024 | 5324/BWD | 01/12/2023 | 30/03/2024 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 0 | 0 | 100
5 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Material Requisition To Resource Division |  |  | RTOR000774/2023-2024 | 207/BWD | 10/01/2024 | 10/01/2024 | Resource Division | 57.55 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Quotation for new service connection at Shilla PWSS (Naba Khanda) Zone-I. |  |  | BILL/00783/2024-2025 | BP-2024-25-290 | 13/09/2024 | 13/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.26 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Quotation for new service connection Shilla PWSS TW No. 3. |  |  | BILL/00781/2024-2025 | BP-2024-25-291 | 13/09/2024 | 13/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.32 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries including intake (Low lift) pumping machineries, illumination arrangement of Shilla Sub-Surface Based Piped Water Supply Scheme under Purba Bardhaman District PHE Dte. | Driller In-Charge | JUNIOR ENGINEER | ORD/000781/2024-2025 | 481/CMD | 06/02/2025 | 22/04/2025 | JAL PRAVAHIKA PVT LTD | 0 | 0 | NAN | 0
9 | PURBA BARDHAMAN | Galsi-I | Burdwan Division | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Sub Surface Based Piped Water Supply Scheme with LDS, FHTC, Construction of different capacity RCC OHRs with 20.0 mtr. with Staging height including soil investigation, Construction of CWR, Chlorine Room, Guard Room, Sub Station Building, High Lift Pump House Boundary walls with gates, land development, drain and internal pathway of SHILLA Piped Water Supply Scheme under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] |  |  | ORD/000455/2023-2024 | 3437/BWD | 08/08/2023 | 01/01/2026 | M/S S. CHOUDHURY | 2687.54 | 0 | 0 | 60
10 | PURBA BARDHAMAN | Galsi-I | Central Mechanical | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for OHR SITE of Zone-1, 2, 3 & 4 at SHILLA Water Supply Scheme [ BLOCK- Galsi-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000561/2024-2025 | 3101/CMD | 11/12/2024 | 29/06/2025 | S.K. ELECTRICALS | 50.24 | 0 | 0 | 46
11 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe Carring Bridge with Pipe supporting structure under SHILLA PIPED W/S SCHMEME under Durgapur W/S Division, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | JUNIOR ENGINEER-1 | ORD/000160/2024-2025 | 1500/DWSD | 05/11/2024 | 01/01/2026 | M/S S. CHOUDHURY | 1099 | 0 | 0 | 45
12 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Acceptance cum Formal Work Order for the work of Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Junior Engineers for the office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.08.2024 to 31.01.2025 (6 Months) | Assistant Engineer-I | JUNIOR ENGINEER-2 | ORD/000121/2024-2025 | 1108/DWSD | 01/08/2024 | 01/02/2025 | SIDDHARTH ENTERPRISE | 0.82 | 0 | 0 | 0
13 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | CONTINUTION ORDER FOR Hiring of LUXURY Disel Ambassador Car (Inspection Vehicle) for using of the Junior Engineers for the Office of the EE, Durgapur W/S Division, PHE Dte at Nababhat, Fagupur, Purba Bardhaman for the period of 01.02.2025 to 30.04.2025. (VEHICLE NO WB/04H-5935) | Assistant Engineer-I | JUNIOR ENGINEER-2 | ORD/000263/2024-2025 | 184/DWSD | 28/01/2025 | 28/04/2025 | SIDDHARTH ENTERPRISE | 0.41 | 0 | 0 | 33
14 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Acceptance cum Formal Work Order for Preparation and Submission of Structural Design Calculation (Civil) & Structural drawing of Proposed CWR with M.S Structural Pump House over cwr, WBSEDCL Mettering Room and - PDB Room -2 Nos, Transformer yeard -2 nos, Chlorin Room -1 No with General Arrangement Drawing of InternalRoad - Drain & necessary Soil investigation at Intake Site of "SHILLA (Zone-I, II, III &IV ) PWSS under Durgapur W/s Division, PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-1,JUNIOR ENGINEER-2 | ORD/000191/2024-2025 | 1606/DWSD | 26/11/2024 | 10/01/2025 | M/S S. CHOUDHURY | 9.48 | 0 | 0 | 100
15 | PURBA BARDHAMAN | Galsi-I | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME | SM/18344 | New | Acceptance cum Formal Work Order for Design Engineering Services of Survey, General arrangement drawing, Pile foundation design and drawings, Pipe Pedestal and BOM, Structural design design and drawing, Fabrication drawings for 26 Numbers different dia meter pipe crossing Pipe Bridge at "PURANGAN (Zone-I, II, III), 11 Nos. Mouzas under PURSHA and UCHCHGRAM, SHILLA (Zone-I, II, III, IV), TAHER PUR (Zone-I, II, III) and KHANO (Zone-I and II) sites under Durgapur W/S Division,PHE Dte. | Assistant Engineer-II | JUNIOR ENGINEER-2 | ORD/000105/2024-2025 | 1058/DWSD | 25/07/2024 | 21/04/2025 | ASTER CONSULTANCY | 47.43 | 0 | 0 | 70
Total | [13 empty] | 4593.08 | 0 | 0