## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | Sanko Piped Water Supply Scheme | SM/18407 | New | Material Requisition To Resource Division |  |  | RTOR000282/2023-2024 | 2197/BWD | 12/05/2023 | 12/05/2023 | Resource Division | 7.07 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Galsi-II | Burdwan Division | Sanko Piped Water Supply Scheme | SM/18407 | New | Material Requisition To Resource Division |  |  | RTOR000445/2023-2024 | 3832/BWD | 01/09/2023 | 01/09/2023 | Resource Division | 191.84 | 0 | 0 | 0
3 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | Sanko Piped Water Supply Scheme | SM/18407 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | ASSISTANT ENGINEER | JUNIOR ENGINEER | ORD/000397/2024-2025 | 2751/CMD | 24/09/2024 | 23/12/2024 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
4 | PURBA BARDHAMAN | Galsi-II | Durgapur W/S Division | Sanko Piped Water Supply Scheme | SM/18407 | New | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 1724/M/DWSD | 10/12/2024 | 10/12/2024 | Resource Division | 16.63 | 0 | 0 | 0
5 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | Sanko Piped Water Supply Scheme | SM/18407 | New | New service connection charges for Sanko PWSS TW-1 |  |  | BILL/02193/2023-2024 | BP-2023-24-373 | 16/01/2024 | 16/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.63 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | Sanko Piped Water Supply Scheme | SM/18407 | New | New service connection for Sanko PWSS . |  |  | BILL/02409/2023-2024 | BP-2023-24-508 | 06/02/2024 | 06/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.1 | 0 | 0 | 0
7 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | Sanko Piped Water Supply Scheme | SM/18407 | New | Quotation for new service connection at Sanko PWSS TW 3 |  |  | BILL/01228/2024-2025 | BP-2024-25-417 | 16/12/2024 | 16/12/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.83 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Galsi-II | Central Mechanical | Sanko Piped Water Supply Scheme | SM/18407 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SANKO Water Supply Scheme [ Block- GALSI-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | Driller In-Charge | JUNIOR ENGINEER | ORD/000782/2023-2024 | 4075/CMD | 29/08/2023 | 05/05/2025 | BENGAL CONSTRUCTION. | 41.68 | 0 | 0 | 96
Total | [13 empty] | 362.2 | 0 | 0